## لوحة الربحية
لوحة الربحية والتكلفة – مشروع سبارك
نسخة إدارية قابلة للتحديث – جميع القيم بالريال السعودي، والمصروفات الإضافية تُسجل في ورقة «المصروفات الإضافية».
قيمة العقد الأصلية | 6493121.74 | قراءة سريعة
أوامر التغيير | 27918 | نسبة الإنجاز التعاقدية | 89.52%
قيمة العقد المعدلة | 6521039.74 | نسبة التكلفة المباشرة من قيمة الأعمال | 67.35%
قيمة الأعمال المنجزة | 5837858.2975 | نقطة الانتباه | أدخل المصروفات غير المباشرة أولاً بأول
تكلفة المواد المباشرة | 3104507 | النتيجة الحالية | الربح الصافي يتغير تلقائياً بعد تسجيل المصروفات
تكلفة العمالة المباشرة | 827570
إجمالي التكلفة المباشرة | 3932077
الربح الفعلي حسب Profit | 2483848.85 | البند | القيمة
المصروفات الإضافية | 549500 | قيمة الأعمال المنجزة | 5837858.2975
الربح الصافي بعد المصروفات الإضافية | 1934348.85 | التكلفة المباشرة | 3932077
هامش الربح الصافي | 33.13% | الربح قبل المصروفات | 2483848.85
|  | المصروفات الإضافية | 549500
|  | الربح بعد المصروفات | 1934348.85

## INVOICE NO 14
Affordable House Co.
CONTRACTORS PAYMENT CERTIFICATE
|  |  |  | Interim Advance Payment | [6 empty] | Interim Progress Payment | [7 empty] | Interim Exchange of Retention
Final Pay and Release of Retention
Contract No. |  | : | C/AHC/PD/C070/2024 | [9 empty] | Contractor's Payment Certificate No. | [6 empty] | : | 14
Consultant |  | : | شركة المسكن الميسر | [13 empty] | Certificate Date |  |  | : | 2026-01-04
Contractor |  | : | مؤسسة أسس السلامة لأجهزة السلامة | [13 empty] | Valuation Date |  |  | :
Project Title |  | : | عقد تنفيذ اعمال إنذار ومكافحة الحريق للمباني وغرف المضخات بالمرحلة الاول PHASE 1مجمع سكن العمال (ECODAN) في مدينة الملك سلمان للطاقة
Original Contract Value | [9 empty] | SR |  | القيمة الأصلية للعقد | [9 empty] | 6493121.74
[12 empty] | أمر تغيير رقم (1) | [9 empty] | 27918
[12 empty] | قيمة الدفعة المقدمة | [9 empty] | 649312.174
Revised Contract Value | [9 empty] | SR |  | اجمالي قيمة العقد | [9 empty] | 6521039.74
Description | [15 empty] | Cumulative To Date (SR) |  | Cumulative Previous (SR) |  |  |  |  | This Payment (SR)
Deserved against Original Contract and Variation Order:
دفعة أولى صرفت مسبقاً | [14 empty] | 10% | 649312.17 |  | 649312.17 |  |  |  |  | 0
قيمة الاعمال المنجزة حتى تاريخه | [14 empty] | 89.52% | 5837858.2975 |  | 4918609.3604 |  |  |  |  | 919248.9371
أمر تغيير رقم (1) | [15 empty] | 27918 |  | 27918
Total Gross Certified | [13 empty] | 99.52% |  | 6515088.4675 |  | 5595839.5304 |  |  |  |  | 919248.9371
Deductions:
On Hold - Best Performance =10% | [15 empty] | 651508.8468 |  | 559583.953 |  |  |  |  | 91924.8937
قيمة غرامة التاخير طبقا للعقد في زون 1 | [15 empty] | 42781.6 |  | 42781.6 |  |  |  |  | 0
استرداد خصم الاستشاري | [15 empty] | -2037.22 |  | -2037.22 |  |  |  |  | 0
Total Deductions | [15 empty] | 692253.2268 |  | 600328.333 |  |  |  |  | 91924.8937
AMOUNT CERTIFIED THIS PAYMENT CERTIFICATE | [15 empty] | 5822835.2408 |  | 4995511.1974 |  |  |  |  | 827324.0434
مائة وإثنان الفا وخمسمائة وخمسة وتسعون ريالا وست وأربعون هللة لا غير
إقرار: إن المقاول يقر بأن قيمة الأعمال الواردة أعلاه في المستخلص هي كل ما لديه من مستحقات لدى شركة المسكن الميسر حتى تاريخ المستخلص، وعلى هذا يوقع
Submitted by Contractor |  |  |  |  | : |  |  |  | (مؤسسة أسس السلامة لأجهزة السلامة) | [6 empty] | Stamp:
Project Manager
Reviewed by consultant |  |  |  |  | : |  |  |  | (مكتب التأثير للاستشارات الهندسية IMPACT) | [6 empty] | Stamp:
Resident Engineer
Certified for Payment by Project Manager | [7 empty] | : | (شركة المسكن الميسر Affordable House)
| Project Manager/ Client Representative | [13 empty] | Acting / Projects Dept. Director
Approved for Payment by Client | [5 empty] | : |  |  | (شركة المسكن الميسر Affordable House)
Acting/CEO

## summary
PAY ITEM NO. | DESCRIPTION OF ITEM |  |  |  | PREVIOUS PRICE (SR) EXCL. VAT | CURRENT PRICE (SR) EXCL. VAT | EXTENDED PRICE (SR) EXCL. VAT | 90% OF PREVIOUS Amount | 90% OF Current Amount | 90% OF CUMULATIVE (10% ADV. PAYMENT)
JUN-T1 | SUB-TOTAL ITEM NO. B1-21 00 00 | xxx | xxx | xxx | 730383.5675 | 29111.8825 | 759495.45 | 657345.2107 | 26200.6942 | 683545.905
JUN-T2 | SUB-TOTAL ITEM NO. B2-21 00 00 | xxx | xxx | xxx | 291679.97 | 6391.33 | 298071.3 | 262511.973 | 5752.197 | 268264.17
SUPRVSR | SUB-TOTAL ITEM NO. B3-21 00 00 | xxx | xxx | xxx | 431679.7009 | 15034.3991 | 446714.1 | 388511.7308 | 13530.9592 | 402042.69
SENIOR | SUB-TOTAL ITEM NO. B4-21 00 00 | xxx | xxx | xxx | 475707.1494 | 16490.2506 | 492197.4 | 428136.4345 | 14841.2255 | 442977.66
ISOLATED | SUB-TOTAL ITEM NO. B6-21 00 00 | xxx | xxx | xxx | 106713.7012 | 7644.4488 | 114358.15 | 96042.3311 | 6880.0039 | 102922.335
ADMIN | SUB-TOTAL ITEM NO. B7-21 00 00 | xxx | xxx | xxx | 131017.9 | 25772.9 | 156790.8 | 117916.11 | 23195.61 | 141111.72
RECREATN | SUB-TOTAL ITEM NO. B8-21 00 00 | xxx | xxx | xxx | 198733.9637 | 36418.2863 | 235152.25 | 178860.5674 | 32776.4576 | 211637.025
SERVICE | SUB-TOTAL ITEM NO. B9-21 00 00 | xxx | xxx | xxx | 428538.4604 | 307168.3896 | 735706.85 | 385684.6143 | 276451.5507 | 662136.165
PUMP RM-2 | SUB-TOTAL ITEM NO. B12-21 00 00 | xxx | xxx | xxx | 439932.4604 | 101885.2896 | 541817.75 | 395939.2144 | 91696.7606 | 487635.975
JUN-T1 - E | SUB-TOTAL ITEM NO. B1-2800 00 | xxx | xxx | xxx | 699685.541 | 122738.659 | 822424.2 | 629716.9869 | 110464.7931 | 740181.78
JUN-T2 - E | SUB-TOTAL ITEM NO. B2-28 00 00 | xxx | xxx | xxx | 191301.46 | 26967.94 | 218269.4 | 172171.314 | 24271.146 | 196442.46
SUPRVSR - E | SUB-TOTAL ITEM NO. B3-28 00 00 | xxx | xxx | xxx | 282927.66 | 62809.44 | 345737.1 | 254634.894 | 56528.496 | 311163.39
SENIOR - E | SUB-TOTAL ITEM NO. B4-28 00 00 | xxx | xxx | xxx | 361496.205 | 45496.395 | 406992.6 | 325346.5845 | 40946.7555 | 366293.34
ISOLATED - E | SUB-TOTAL ITEM NO. B6-28 00 00 | xxx | xxx | xxx | 105596.237 | -11312.237 | 94284 | 95036.6133 | -10181.0133 | 84855.6
ADMIN - E | SUB-TOTAL ITEM NO. B7-28 00 00 | xxx | xxx | xxx | 67078.41 | 79168.49 | 146246.9 | 60370.569 | 71251.641 | 131622.21
RECREATN - E | SUB-TOTAL ITEM NO. B8-28 00 00 | xxx | xxx | xxx | 131764.8 | 18517.3 | 150282.1 | 118588.32 | 16665.57 | 135253.89
SERVICE - E | SUB-TOTAL ITEM NO. B9-28 00 00 | xxx | xxx | xxx | 187954.475 | 109690.025 | 297644.5 | 169159.0275 | 98721.0225 | 267880.05
GUARD RM | SUB-TOTAL ITEM NO. B10-28 00 00 | xxx | xxx | xxx | 27603.775 | 18762.225 | 46366 | 24843.3975 | 16886.0025 | 41729.4
PUMP RM-1 | SUB-TOTAL ITEM NO. B11-28 00 00 | xxx | xxx | xxx | 0 | 2910 | 2910 | 0 | 2619 | 2619
PUMP RM-2 | SUB-TOTAL ITEM NO. B12-28 00 00 | xxx | xxx | xxx | 0 | 11640 | 11640 | 0 | 10476 | 10476
PUMP RM-3 | SUB-TOTAL ITEM NO. B13-28 00 00 | xxx | xxx | xxx | 0 | 2910 | 2910 | 0 | 2619 | 2619
JUN-T1-EXT | SUB-TOTAL ITEM NO. B1-10 00 00 | xxx | xxx | xxx | 76242 | 0 | 76242 | 68617.8 | 0 | 68617.8
JUN-T2-EXT | SUB-TOTAL ITEM NO. B2-10 00 00 | xxx | xxx | xxx | 11441.65 | 4175.85 | 15617.5 | 10297.485 | 3758.265 | 14055.75
SUPERVISOR-EXT | SUB-TOTAL ITEM NO. B3-10 00 00 | xxx | xxx | xxx | 19999.225 | 7670.275 | 27669.5 | 17999.3025 | 6903.2475 | 24902.55
SENIOR-EXT | SUB-TOTAL ITEM NO. B4-10 00 00 | xxx | xxx | xxx | 15447 | 2500 | 17947 | 13902.3 | 2250 | 16152.3
ISOLATED-EXT | SUB-TOTAL ITEM NO. B6-10 00 00 | xxx | xxx | xxx | 5322.95 | 2048.05 | 7371 | 4790.655 | 1843.245 | 6633.9
ADMIN-EXT | SUB-TOTAL ITEM NO. B7-10 00 00 | xxx | xxx | xxx | 2863.8 | 2192.2 | 5056 | 2577.42 | 1972.98 | 4550.4
RECREATION-EXT | SUB-TOTAL ITEM NO. B8-10 00 00 | xxx | xxx | xxx | 10628 | 4285 | 14913 | 9565.2 | 3856.5 | 13421.7
SERVICE-EXT | SUB-TOTAL ITEM NO. B9-10 00 00 | xxx | xxx | xxx | 21367.5 | 14557.5 | 35925 | 19230.75 | 13101.75 | 32332.5
GUARD-RM-EXT | SUB-TOTAL ITEM NO. B10-10 00 00 | xxx | xxx | xxx | 434.2 | 196.425 | 630.625 | 390.78 | 176.7825 | 567.5625
PUMP-R1-EXT | SUB-TOTAL ITEM NO. B11-10 00 00 | xxx | xxx | xxx | 5761.925 | 10631.2 | 16393.125 | 5185.7325 | 9568.08 | 14753.8125
PUMP-R21-EXT | SUB-TOTAL ITEM NO. B12-10 00 00 | xxx | xxx | xxx | 465.725 | 196.425 | 662.15 | 419.1525 | 176.7825 | 595.935
PUMP-R3-EXT | SUB-TOTAL ITEM NO. B13-10 00 00 | xxx | xxx | xxx | 5352.1 | 2844.525 | 8196.625 | 4816.89 | 2560.0725 | 7376.9625
Variance between the total quantities amount and the contract amount | [6 empty] | -59512.64 |  | -59512.64 | -59512.64
| TOTAL ESTIMATED CONTRACT PRICE FOR PAY ITEM NO. B1 | xxx | xxx | xxx | 5465121.5116 | 1087512.8634 | 6493121.735 | 4918609.3604 | 919248.9371 | 5837858.2975
| % of Completion | [5 empty] | 100%
6493121.74
-0.005
-59512.635

## JUN-T1 E
JUN T1 E
| B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR)
DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative | Percentage | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 28-ELECTRONIC SAFETY AND SECURITY
Supply and installation of IP Fixed cameras, POE+ TCP/IP and IP Indoor fixed mini dome camera-ceiling mounted, including all accessories, testing, commissioning and configuration of the network and other Works as shown on the Contract drawings and specified in the Contract documents.
Fire Detection and Alarm
Fire alarm control panel (FACP)
Supply, installation, testing and commissioning of a microprocessor based, addressable fire alarm control panel, complete with Chassis, 640-Character backlit LCD display, QWERTY programming and control keypad, loop cards, zone and input/output modules, supervisory devices, auxiliary relays, network capability modules, battery, battery charger, printer, internal alarm, interface contacts and all accessories and hardware as shown on the Contract drawings and specified in the Contract documents and to complete the fully functional, operable, reliable and maintainable fire alarm system.
Microprocessor based, addressable FACP,5 loop type | 12 | Ea | 22795 | 10.8 | 1.2 | 12 | 246186 | 27354 | 273540 | 100% | 16900 | 80 | 203760 | 69780
Power supply unit, batteries and battery chargers | 12 | Ea | 4365 | 0 | 12 | 12 | 0 | 52380 | 52380 | 100% | 0 | 0 | 0 | 52380
Supply, selection and calculation, installation, testing and commissioning of FACP power supply unit, batteries for at least 24 hours during the normal operations and 15 mins under emergency full loaded condition. Provide separate combination of power Supply and battery enclosure when large batteries are required and not be able embedded inside FACP panel.
Detection and initiation devices
Supply, installation, testing and commissioning of intelligent, addressable type fire alarm detectors and initiating devices as shown on the Contract drawings and specified in the Contract documents complete with all mounting accessories including boxes, connectors and terminations.
Smoke detector - photoelectric, addressable, self diagnostic, self address | 747 | Ea | 339.5 | 672.3 | 74.7 | 747 | 228245.85 | 25360.65 | 253606.5 | 100% | 120 | 80 | 149400 | 104206.5
Heat detector - rate of rise type with fix temperature | 36 | Ea | 339.5 | 32.4 | 3.6 | 36 | 10999.8 | 1222.2 | 12222 | 100% | 110 | 80 | 6840 | 5382
Addressable manual fire alarm pull station | 72 | Ea | 291 | 64.8 | 7.2 | 72 | 18856.8 | 2095.2 | 20952 | 100% | 160 | 80 | 17280 | 3672
Addressable manual fire alarm pull station, weather proof | 27 | Ea | 368.6 | 24.21 | 2.79 | 27 | 8923.806 | 1028.394 | 9952.2 | 100% | 180 | 80 | 7020 | 2932.2
Other initiating devices and control devices
Supply, Installation, testing and commissioning of all conventional I/O interfaces devices for interface and Integration with firefighting systems, gas alarm and control systems, lift safety devices, fire water pumps, HVAC systems. elevators and all other specified equipment as per contract drawings and specifications, complete with all mounting accessories including boxes and terminations.
Fire alarm monitoring module (MM) | 24 | Ea | 436.5 | 21.52 | 2.48 | 24 | 9393.48 | 1082.52 | 10476 | 100% | 140 | 80 | 5280 | 5196
Notification appliances
Supply, installation, testing and commissioning of visual and sound alarm devices as shown on the Contract drawings and specified in the Contract documents complete with all mounting accessories including boxes and terminations.
Bells, indoor with strobe lights / beacons - red body, red lens for fire alarm | 84 | Ea | 388 | 75.6 | 8.4 | 84 | 29332.8 | 3259.2 | 32592 | 100% | 212 | 80 | 24528 | 8064
Bells, indoor with strobe lights / beacons - red body, red lens for fire alarm, weather proof | 39 | Ea | 436.5 | 34.97 | 4.03 | 39 | 15264.405 | 1759.095 | 17023.5 | 100% | 250 | 80 | 12870 | 4153.5
Fire alarm cables - fire resistant cable, 300V/500V, red sheath with low emission of smoke, halogen free, thermoplastic material
To include for the procurement, supply, factory testing, delivery to Site, installation, testing and commissioning of the cables, termination materials and all cable support and wiring, identification accessories.
2C x 2.5 mm², Stranded plain copper wire or solid conductor, overall shield with drain wire for SLC loop | 3915 | m | 24.25 | 3706.2 | 208.8 | 3915 | 89875.35 | 5063.4 | 94938.75 | 100% | 8 | 0 | 31320 | 63618.75
2C x 2.5 mm², Stranded plain copper wire or solid conductor, overall shield with drain wire for NAC Loop | 1845 | m | 24.25 | 1757 | 88 | 1845 | 42607.25 | 2134 | 44741.25 | 100% | 8 | 0 | 14760 | 29981.25
Fire alarm cable conduit, all JB boxes, fittings and accessories for cable installations
To include for the procurement, supply, installation of PVC conduits and flexible metallic conduits for fire cables, junction boxes, fittings, accessories and all other relevant items or Works to complete fully Fire alarm detection system installations.
20 mm diameter, PVC conduits | 0 | m | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
SUB-TOTAL ITEM NO. B1-28 00 00 | xxx | xxx |  |  |  |  | 699685.541 | 122738.659 | 822424.2 |  |  |  | 473058 | 349366.2
(TO BE CARRIED TO COMPOSITE SUMMARY)
OWNER | CONSULTANT | [5 empty] | CONTRACTOR

## JUN-T1-EXT
JUN-T1
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR) |  |  | Percentage
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative |  | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 10 - SPECIALTIES
1.0 | Fire Extinguishers
Includes mounting brackets, fasteners, service tags, fully charged and ready to use extinguishers.
a. | Multipurpose dry chemical type, UL rated ABC
a.1 | FE-1, 6 kg, multi purpose fire extinguisher | 96 | Ea | 242.5 | 96 | 0 | 96 | 23280 | 0 | 23280 | 100% | 240 | 10 | 24000 | -720
b. | Wet chemical type, UL rated class K
b.1 | FE-3, kitchen type-K fire extinguisher 2 gallon | 36 | Ea | 533.5 | 36 | 0 | 36 | 19206 | 0 | 19206 | 100% | 320 | 10 | 11880 | 7326
c. | Automatic fire extinguisher
c.1 | FE-2, 12 kg, multi purpose fire extinguisher, ceiling mounted | 48 | Ea | 485 | 48 | 0 | 48 | 23280 | 0 | 23280 | 100% | 304 | 10 | 15072 | 8208
d. | Fire blanket
Supply and installation of fire blanket of specified type to be located in kitchen with all fittings and supports required to provide satisfactory operation.
d.1 | Fire blanket, standard size (1.2 meter x 1.2 meter), NFPA approved | 36 | Ea | 291 | 36 | 0 | 36 | 10476 | 0 | 10476 | 100% | 16 | 10 | 936 | 9540
| SUB-TOTAL ITEM NO. B1-10 00 00 | xxx | xxx |  |  |  |  | 76242 | 0 | 76242 |  |  |  | 51888 | 24354

## JUN-T1
JUN T1
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR) |  |  | Percentage
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative |  | Actual price | accessories | Actual Labour charge | Total AP+LC | Profit
DIVISION 21 - FIRE SUPPRESSION
1.0 | General-Duty Valves for Water-Based Fire-Suppression Piping
Supply and installation of valves including all fixings, supports, all other accessories and associated Works.
a. | Gate valve, UL and FM global approved
a.1 | 150 mm diameter | 6 | Ea | 3686 | 5.2 | 0.8 | 6 | 19167.2 | 2948.8 | 22116 | 100% | 1250 | 100 | 300 | 9900 | 12216
b. | Alarm check valve, UL and FM global approved
b.1 | 150 mm diameter | 3 | Ea | 5577.5 | 2.3 | 0.7 | 3 | 12828.25 | 3904.25 | 16732.5 | 100% | 3830 | 200 | 100 | 12390 | 4342.5
c. | Zone control valve assembly
c.1 | 100 mm diameter | 9 | Ea | 5626 | 7.8 | 1.2 | 9 | 43882.8 | 6751.2 | 50634 | 100% | 3000 | 150 | 100 | 29250 | 21384
2.0 | Fire-Department Connections
Two way, swivel fittings, Dust caps and chains of same material as body, chrome plated finish and threads to match local fire department hardware
a. | Flush wall mounted fire department connection with check valve
a.1 | Two-way swivel fittings, 65 x 65 x 100 mm single clapper Siamese-type connections | 3 | Ea | 4462 | 1.95 | 1.05 | 3 | 8700.9 | 4685.1 | 13386 | 100% | 450 | 150 | 100 | 2100 | 11286
3.0 | Wet-Pipe Sprinkler Systems
a. | Black steel fire water pipes
Supply and installation of black steel pipe seamless type as per ASTM A53 including supports, hangers, fixing, fitting, all other accessories and associated Works as per Contract drawings and specifications.
a.1 | 25 mm diameter | 2550 | m | 53.35 | 2550 | 0 | 2550 | 136042.5 | 0 | 136042.5 | 100% | 15 | 7.5 | 0 | 57375 | 78667.5
a.2 | 32 mm diameter | 375 | m | 63.05 | 375 | 0 | 375 | 23643.75 | 0 | 23643.75 | 100% | 20 | 10 | 0 | 11250 | 12393.75
a.3 | 40 mm diameter | 276 | m | 77.6 | 276 | 0 | 276 | 21417.6 | 0 | 21417.6 | 100% | 24 | 12 | 0 | 9936 | 11481.6
a.4 | 50 mm diameter | 90 | m | 95.06 | 90 | 0 | 90 | 8555.4 | 0 | 8555.4 | 100% | 28 | 14 | 0 | 3780 | 4775.4
a.5 | 65 mm diameter | 30 | m | 169.75 | 30 | 0 | 30 | 5092.5 | 0 | 5092.5 | 100% | 30 | 15 | 0 | 1350 | 3742.5
a.6 | 80 mm diameter | 30 | m | 190.12 | 30 | 0 | 30 | 5703.6 | 0 | 5703.6 | 100% | 35 | 25 | 0 | 1800 | 3903.6
a.7 | 100 mm diameter | 450 | m | 237.65 | 450 | 0 | 450 | 106942.5 | 0 | 106942.5 | 100% | 90 | 60 | 0 | 67500 | 39442.5
a.8 | 150 mm diameter | 120 | m | 344.35 | 120 | 0 | 120 | 41322 | 0 | 41322 | 100% | 170 | 90 | 0 | 31200 | 10122
b. | Fire water sprinkler head
Sprinkler Head, UL listed FM approved, chrome-plated, bronze and factory painted; Shall be of one manufacturer. (No mixing of sprinkler brands shall be permitted).
b.1 | Pendent type | 750 | Ea | 63.05 | 651.95 | 98.05 | 750 | 41105.4475 | 6182.0525 | 47287.5 | 100% | 25 | 5 | 100 | 97500 | -50212.5
b.2 | Upright type | 48 | Ea | 33.95 | 41.6 | 6.4 | 48 | 1412.32 | 217.28 | 1629.6 | 100% | 19 | 5 | 100 | 5952 | -4322.4
b.3 | Wall side type | 456 | Ea | 72.75 | 395.2 | 60.8 | 456 | 28750.8 | 4423.2 | 33174 | 100% | 59 | 5 | 100 | 74784 | -41610
4.0 | Fire-Suppression Standpipes
a. | Fire Hose Cabinet
Supply and installation of Surface mounted fire hose Cabinets Made of Stainless Steel, dimension (W 750 x H 850 x D 180). with Synthetic Single Jacket Hose 1.5” x 30 meter long and (1) multipurpose dry powder Extinguisher include fittings, joints, unions, dielectric fittings, flanges, gaskets, grooved mechanical couplings, nuts and bolts, hangers and supports and labelling.
a.1 | FHC-II | 48 | Ea | 4704.5 | 48 | 0 | 48 | 225816 | 0 | 225816 | 100% | 4200 | 250 | 400 | 232800 | -6984
| SUB-TOTAL ITEM NO. B1-21 00 00 | xxx | xxx |  |  |  |  | 730383.5675 | 29111.8825 | 759495.45 |  |  |  |  | 648867 | 110628.45
(TO BE CARRIED TO COMPOSITE SUMMARY)
| OWNER | CONSULTANT | [5 empty] | CONTRACTOR

## JUN-T2 E
JUN T2 - E
| B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR)
DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative | Percentage | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 28-ELECTRONIC SAFETY AND SECURITY
Supply and installation of IP Fixed cameras, POE+ TCP/IP and IP Indoor fixed mini dome camera-ceiling mounted, including all accessories, testing, commissioning and configuration of the network and other Works as shown on the Contract drawings and specified in the Contract documents.
Fire Detection and Alarm
Fire alarm control panel (FACP)
Supply, installation, testing and commissioning of a microprocessor based, addressable fire alarm control panel, complete with Chassis, 640-Character backlit LCD display, QWERTY programming and control keypad, loop cards, zone and input/output modules, supervisory devices, auxiliary relays, network capability modules, battery, battery charger, printer, internal alarm, interface contacts and all accessories and hardware as shown on the Contract drawings and specified in the Contract documents and to complete the fully functional, operable, reliable and maintainable fire alarm system.
Microprocessor based, addressable FACP,5 loop type | 2 | Ea | 22795 | 1.8 | 0.2 | 2 | 41031 | 4559 | 45590 | 100% | 16900 | 80 | 33960 | 11630
Power supply unit, batteries and battery chargers | 2 | Ea | 4365 | 0 | 2 | 2 | 0 | 8730 | 8730 | 100% | 0 | 0 | 0 | 8730
Supply, selection and calculation, installation, testing and commissioning of FACP power supply unit, batteries for at least 24 hours during the normal operations and 15 mins under emergency full loaded condition. Provide separate combination of power Supply and battery enclosure when large batteries are required and not be able embedded inside FACP panel.
Detection and initiation devices
Supply, installation, testing and commissioning of intelligent, addressable type fire alarm detectors and initiating devices as shown on the Contract drawings and specified in the Contract documents complete with all mounting accessories including boxes, connectors and terminations.
Smoke detector - photoelectric, addressable, self diagnostic, self address | 244 | Ea | 339.5 | 219.6 | 24.4 | 244 | 74554.2 | 8283.8 | 82838 | 100% | 120 | 80 | 48800 | 34038
Heat detector - rate of rise type with fix temperature | 6 | Ea | 339.5 | 5.4 | 0.6 | 6 | 1833.3 | 203.7 | 2037 | 100% | 110 | 80 | 1140 | 897
Addressable manual fire alarm pull station | 12 | Ea | 291 | 10.8 | 1.2 | 12 | 3142.8 | 349.2 | 3492 | 100% | 160 | 80 | 2880 | 612
Addressable manual fire alarm pull station, weather proof | 4 | Ea | 368.6 | 3.6 | 0.4 | 4 | 1326.96 | 147.44 | 1474.4 | 100% | 180 | 80 | 1040 | 434.4
Other initiating devices and control devices |  |  |  |  | 0
Supply, Installation, testing and commissioning of all conventional I/O interfaces devices for interface and Integration with firefighting systems, gas alarm and control systems, lift safety devices, fire water pumps, HVAC systems. elevators and all other specified equipment as per contract drawings and specifications, complete with all mounting accessories including boxes and terminations. |  |  |  |  | 0
Fire alarm monitoring module (MM) | 16 | Ea | 436.5 | 14.4 | 1.6 | 16 | 6285.6 | 698.4 | 6984 | 100% | 140 | 80 | 3520 | 3464
Notification appliances |  |  |  |  | 0
Supply, installation, testing and commissioning of visual and sound alarm devices as shown on the Contract drawings and specified in the Contract documents complete with all mounting accessories including boxes and terminations. |  |  |  |  | 0
Bells, indoor with strobe lights / beacons - red body, red lens for fire alarm | 14 | Ea | 388 | 12.6 | 1.4 | 14 | 4888.8 | 543.2 | 5432 | 100% | 212 | 80 | 4088 | 1344
Bells, indoor with strobe lights / beacons - red body, red lens for fire alarm, weather proof | 8 | Ea | 436.5 | 7.2 | 0.8 | 8 | 3142.8 | 349.2 | 3492 | 100% | 250 | 80 | 2640 | 852
Fire alarm cables - fire resistant cable, 300V/500V, red sheath with low emission of smoke, halogen free, thermoplastic material |  |  |  |  | 0
To include for the procurement, supply, factory testing, delivery to Site, installation, testing and commissioning of the cables, termination materials and all cable support and wiring, identification accessories. |  |  |  |  | 0
2C x 2.5 mm², Stranded plain copper wire or solid conductor, overall shield with drain wire for SLC loop | 1600 | m | 24.25 | 1514.6667 | 85.3333 | 1600 | 36730.6667 | 2069.3333 | 38800 | 100% | 8 | 0 | 12800 | 26000
2C x 2.5 mm², Stranded plain copper wire or solid conductor, overall shield with drain wire for NAC Loop | 800 | m | 24.25 | 757.3333 | 42.6667 | 800 | 18365.3333 | 1034.6667 | 19400 | 100% | 8 | 0 | 6400 | 13000
Fire alarm cable conduit, all JB boxes, fittings and accessories for cable installations
To include for the procurement, supply, installation of PVC conduits and flexible metallic conduits for fire cables, junction boxes, fittings, accessories and all other relevant items or Works to complete fully Fire alarm detection system installations.
20 mm diameter, PVC conduits | 0 | m | 24.25 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
SUB-TOTAL ITEM NO. B1-28 00 00 | xxx | xxx |  |  |  |  | 191301.46 | 26967.94 | 218269.4 |  |  |  | 117268 | 101001.4
(TO BE CARRIED TO COMPOSITE SUMMARY)
OWNER | CONSULTANT | [5 empty] | CONTRACTOR

## JUN-T2-EXT
JUN-T2
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR) |  |  | Percentage
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative |  | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 10 - SPECIALTIES
1.0 | Fire Extinguishers
Includes mounting brackets, fasteners, service tags, fully charged and ready to use extinguishers.
a. | Multipurpose dry chemical type, UL rated ABC
a.1 | FE-1, 6 kg, multi purpose fire extinguisher | 28 | Ea | 242.5 | 21 | 7 | 28 | 5092.5 | 1697.5 | 6790 | 100% | 240 | 10 | 7000 | -210
b. | Wet chemical type, UL rated class K
b.1 | FE-3, kitchen type-K fire extinguisher 2 gallon | 6 | Ea | 533.5 | 3.9 | 2.1 | 6 | 2080.65 | 1120.35 | 3201 | 100% | 320 | 10 | 1980 | 1221
c. | Automatic fire extinguisher
c.1 | FE-2, 12 kg, multi purpose fire extinguisher, ceiling mounted | 8 | Ea | 485 | 5.2 | 2.8 | 8 | 2522 | 1358 | 3880 | 100% | 304 | 10 | 2512 | 1368
d. | Fire blanket
Supply and installation of fire blanket of specified type to be located in kitchen with all fittings and supports required to provide satisfactory operation.
d.1 | Fire blanket, standard size (1.2 meter x 1.2 meter), NFPA approved | 6 | Ea | 291 | 6 | 0 | 6 | 1746 | 0 | 1746 | 100% | 16 | 10 | 156 | 1590
| SUB-TOTAL ITEM NO. B2-10 00 00 | xxx | xxx |  |  |  |  | 11441.15 | 4175.85 | 15617 |  |  |  | 11648 | 3969

## JUN-T2
JUN-T2
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR)
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative | Percentage | Actual price | accessories | Actual Labour charge | Total AP+LC | Profit
DIVISION 21 - FIRE SUPPRESSION
1.0 | General-Duty Valves for Water-Based Fire-Suppression Piping
Supply and installation of valves including all fixings, supports, all other accessories and associated Works.
a. | Gate valve, UL and FM global approved
a.1 | 150 mm diameter | 4 | Ea | 3686 | 3.6 | 0.4 | 4 | 13269.6 | 1474.4 | 14744 | 100% | 1250 | 100 | 300 | 6600 | 8144
b. | Alarm check valve, UL and FM global approved
b.1 | 150 mm diameter | 2 | Ea | 5577.5 | 1.8 | 0.2 | 2 | 10039.5 | 1115.5 | 11155 | 100% | 3830 | 200 | 100 | 8260 | 2895
c. | Zone control valve assembly |  |  |  |  | 0
c.1 | 100 mm diameter | 12 | Ea | 5626 | 11.97 | 0.03 | 12 | 67343.22 | 168.78 | 67512 | 100% | 3000 | 150 | 100 | 39000 | 28512
2.0 | Fire-Department Connections |  |  |  |  | 0
| Two way, swivel fittings, Dust caps and chains of same material as body, chrome plated finish and threads to match local fire department hardware |  |  |  |  | 0
a. | Flush wall mounted fire department connection with check valve |  |  |  |  | 0
a.1 | Two-way swivel fittings, 65 x 65 x 100 mm single clapper Siamese-type connections | 2 | Ea | 4462 | 1.8 | 0.2 | 2 | 8031.6 | 892.4 | 8924 | 100% | 450 | 150 | 100 | 1400 | 7524
3.0 | Wet-Pipe Sprinkler Systems |  |  |  |  | 0
a. | Black steel fire water pipes |  |  |  |  | 0
| Supply and installation of black steel pipe seamless type as per ASTM A53 including supports, hangers, fixing, fitting, all other accessories and associated Works as per Contract drawings and specifications. |  |  |  |  | 0
a.1 | 25 mm diameter | 520 | m | 53.35 | 520 | 0 | 520 | 27742 | 0 | 27742 | 100% | 15 | 7.5 | 0 | 11700 | 16042
a.2 | 32 mm diameter | 120 | m | 63.05 | 120 | 0 | 120 | 7566 | 0 | 7566 | 100% | 20 | 10 | 0 | 3600 | 3966
a.3 | 40 mm diameter | 20 | m | 77.6 | 20 | 0 | 20 | 1552 | 0 | 1552 | 100% | 24 | 12 | 0 | 720 | 832
a.4 | 50 mm diameter | 130 | m | 95.06 | 130 | 0 | 130 | 12357.8 | 0 | 12357.8 | 100% | 28 | 14 | 0 | 5460 | 6897.8
a.5 | 63 mm diameter | 190 | m | 169.75 | 190 | 0 | 190 | 32252.5 | 0 | 32252.5 | 100% | 30 | 15 | 0 | 8550 | 23702.5
a.6 | 80 mm diameter | 50 | m | 190.12 | 50 | 0 | 50 | 9506 | 0 | 9506 | 100% | 35 | 25 | 0 | 3000 | 6506
a.7 | 100 mm diameter | 30 | m | 237.65 | 30 | 0 | 30 | 7129.5 | 0 | 7129.5 | 100% | 90 | 60 | 0 | 4500 | 2629.5
a.8 | 150 mm diameter | 40 | m | 344.35 | 40 | 0 | 40 | 13774 | 0 | 13774 | 100% | 170 | 90 | 0 | 10400 | 3374
b. | Fire water sprinkler head |  |  |  |  | 0
| Sprinkler Head, UL listed FM approved, chrome-plated, bronze and factory painted; Shall be of one manufacturer. (No mixing of sprinkler brands shall be permitted). |  |  |  |  | 0
b.1 | Pendent type | 218 | Ea | 63.05 | 196.2 | 21.8 | 218 | 12370.41 | 1374.49 | 13744.9 | 100% | 25 | 5 | 100 | 28340 | -14595.1
b.2 | Upright type | 8 | Ea | 33.95 | 7.2 | 0.8 | 8 | 244.44 | 27.16 | 271.6 | 100% | 19 | 5 | 100 | 992 | -720.4
b.3 | Wall side type | 184 | Ea | 72.75 | 165.6 | 18.4 | 184 | 12047.4 | 1338.6 | 13386 | 100% | 59 | 5 | 100 | 30176 | -16790
4.0 | Fire-Suppression Standpipes |  |  |  |  | 0
a. | Fire Hose Cabinet |  |  |  |  | 0
| Supply and installation of Surface mounted fire hose Cabinets Made of Stainless Steel, dimension (W 750 x H 850 x D 180). with Synthetic Single Jacket Hose 1.5” x 30 meter long and (1) multipurpose dry powder Extinguisher include fittings, joints, unions, dielectric fittings, flanges, gaskets, grooved mechanical couplings, nuts and bolts, hangers and supports and labelling. |  |  |  |  | 0
a.1 | FHC-II | 12 | Ea | 4704.5 | 12 | 0 | 12 | 56454 | 0 | 56454 | 100% | 4200 | 250 | 400 | 58200 | -1746
| SUB-TOTAL ITEM NO. B2-21 00 00 | xxx | xxx |  |  |  |  | 291679.97 | 6391.33 | 298071.3 |  |  |  |  | 220898 | 77173.3
(TO BE CARRIED TO COMPOSITE SUMMARY)
| OWNER | CONSULTANT | [7 empty] | CONTRACTOR

## SUPERVISOR -E
SUPERVISOR - E
| B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR)
DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative | Percentage | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 28-ELECTRONIC SAFETY AND SECURITY
Fire Detection and Alarm
Fire alarm control panel (FACP)
Supply, installation, testing and commissioning of a microprocessor based, addressable fire alarm control panel, complete with Chassis, 640-Character backlit LCD display, QWERTY programming and control keypad, loop cards, zone and input/output modules, supervisory devices, auxiliary relays, network capability modules, battery, battery charger, printer, internal alarm, interface contacts and all accessories and hardware as shown on the Contract drawings and specified in the Contract documents and to complete the fully functional, operable, reliable and maintainable fire alarm system.
Microprocessor based, addressable FACP, 5 loop type | 3 | Ea | 22795 | 2.45 | 0.55 | 3 | 55847.75 | 12537.25 | 68385 | 100% | 16900 | 80 | 50940 | 17445
Power supply unit, batteries and battery chargers | 3 | Ea | 4365 | 0 | 3 | 3 | 0 | 13095 | 13095 | 100% | 0 | 0 | 0 | 13095
Supply, selection and calculation, installation, testing and commissioning of FACP power supply unit, batteries for at least 24 hours during the normal operations and 15 mins under emergency full loaded condition. Provide separate combination of power Supply and battery enclosure when large batteries are required and not be able embedded inside FACP panel. | [12 empty] | 0 | 0
Detection and initiation devices | [12 empty] | 0 | 0
Supply, installation, testing and commissioning of intelligent, addressable type fire alarm detectors and initiating devices as shown on the Contract drawings and specified in the Contract documents complete with all mounting accessories including boxes, connectors and terminations. |  |  |  |  | 0 | [7 empty] | 0 | 0
Smoke detector - photoelectric, addressable, self diagnostic, self address | 420 | Ea | 339.5 | 343 | 77 | 420 | 116448.5 | 26141.5 | 142590 | 100% | 120 | 80 | 84000 | 58590
Heat detector - rate of rise type with fix temperature | 9 | Ea | 339.5 | 6.26 | 2.74 | 9 | 2125.27 | 930.23 | 3055.5 | 100% | 110 | 80 | 1710 | 1345.5
Addressable manual fire alarm pull station | 18 | Ea | 291 | 14.7 | 3.3 | 18 | 4277.7 | 960.3 | 5238 | 100% | 160 | 80 | 4320 | 918
Addressable manual fire alarm pull station, weather proof | 6 | Ea | 368.6 | 4.9 | 1.1 | 6 | 1806.14 | 405.46 | 2211.6 | 100% | 180 | 80 | 1560 | 651.6
Other initiating devices and control devices |  |  |  |  | 0 | [7 empty] | 0 | 0
Supply, Installation, testing and commissioning of all conventional I/O interfaces devices for interface and Integration with firefighting systems, gas alarm and control systems, lift safety devices, fire water pumps, HVAC systems. elevators and all other specified equipment as per contract drawings and specifications, complete with all mounting accessories including boxes and terminations. |  |  |  |  | 0 | [7 empty] | 0 | 0
Fire alarm monitoring module (MM) | 24 | Ea | 436.5 | 19.6 | 4.4 | 24 | 8555.4 | 1920.6 | 10476 | 100% | 140 | 80 | 5280 | 5196
Notification appliances | [12 empty] | 0 | 0
Supply, installation, testing and commissioning of visual and sound alarm devices as shown on the Contract drawings and specified in the Contract documents complete with all mounting accessories including boxes and terminations. | [12 empty] | 0 | 0
Bells, indoor with strobe lights / beacons - red body, red lens for fire alarm | 21 | Ea | 388 | 17.15 | 3.85 | 21 | 6654.2 | 1493.8 | 8148 | 100% | 212 | 80 | 6132 | 2016
Bells, indoor with strobe lights / beacons - red body, red lens for fire alarm, weather proof | 12 | Ea | 436.5 | 9.8 | 2.2 | 12 | 4277.7 | 960.3 | 5238 | 100% | 250 | 80 | 3960 | 1278
Fire alarm cables - fire resistant cable, 300V/500V, red sheath with low emission of smoke, halogen free, thermoplastic material |  |  |  |  | 0 | [7 empty] | 0 | 0
To include for the procurement, supply, factory testing, delivery to Site, installation, testing and commissioning of the cables, termination materials and all cable support and wiring, identification accessories. |  |  |  |  | 0 | [7 empty] | 0 | 0
2C x 2.5 mm², Stranded plain copper wire or solid conductor, overall shield with drain wire for SLC loop | 2400 | m | 24.25 | 2280 | 120 | 2400 | 55290 | 2910 | 58200 | 100% | 8 | 0 | 19200 | 39000
2C x 2.5 mm², Stranded plain copper wire or solid conductor, overall shield with drain wire for NAC Loop | 1200 | m | 24.25 | 1140 | 60 | 1200 | 27645 | 1455 | 29100 | 100% | 8 | 0 | 9600 | 19500
Fire alarm cable conduit, all JB boxes, fittings and accessories for cable installations |  |  |  |  | 0 | [7 empty] | 0 | 0
To include for the procurement, supply, installation of PVC conduits and flexible metallic conduits for fire cables, junction boxes, fittings, accessories and all other relevant items or Works to complete fully Fire alarm detection system installations. |  |  |  |  | 0 | [7 empty] | 0 | 0
20 mm diameter, PVC conduits | 0 | m | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
SUB-TOTAL ITEM NO. B1-28 00 00 | xxx | xxx |  | 0 | #VALUE! | #VALUE! | 282927.66 | 62809.44 | 345737.1 |  |  |  | 186702 | 159035.1
(TO BE CARRIED TO COMPOSITE SUMMARY)
OWNER | CONSULTANT | [5 empty] | CONTRACTOR

## SUPERVISOR-EXT
SUPERVISOR
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR) |  |  | Percentage
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative |  | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 10 - SPECIALTIES
1.0 | Fire Extinguishers
Includes mounting brackets, fasteners, service tags, fully charged and ready to use extinguishers.
a. | Multipurpose dry chemical type, UL rated ABC
a.1 | FE-1, 6 kg, multi purpose fire extinguisher | 42 | Ea | 242.5 | 32 | 10 | 42 | 7760 | 2425 | 10185 | 100% | 240 | 10 | 10500 | -315
b. | Wet chemical type, UL rated class K
b.1 | FE-3, kitchen type-K fire extinguisher 2 gallon | 9 | Ea | 533.5 | 5.85 | 3.15 | 9 | 3120.975 | 1680.525 | 4801.5 | 100% | 320 | 10 | 2970 | 1831.5
c. | Automatic fire extinguisher
c.1 | FE-2, 15 kg, multi purpose fire extinguisher, ceiling mounted | 21 | Ea | 485 | 13.65 | 7.35 | 21 | 6620.25 | 3564.75 | 10185 | 100% | 334 | 10 | 7224 | 2961
d. | Fire blanket
Supply and installation of fire blanket of specified type to be located in kitchen with all fittings and supports required to provide satisfactory operation.
d.1 | Fire blanket, standard size (1.2 meter x 1.2 meter), NFPA approved | 9 | Ea | 291 | 9 | 0 | 9 | 2619 | 0 | 2619 | 100% | 16 | 10 | 234 | 2385
| SUB-TOTAL ITEM NO. B3-10 00 00 | xxx | xxx |  |  |  |  | 20120.225 | 7670.275 | 27790.5 |  |  |  | 20928 | 6862.5

## SUPERVISOR
SUPERVISOR
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR)
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative | Percentage | Actual price | accessories | Actual Labour charge | Total AP+LC | Profit
DIVISION 21 - FIRE SUPPRESSION
1.0 | General-Duty Valves for Water-Based Fire-Suppression Piping
Supply and installation of valves including all fixings, supports, all other accessories and associated Works.
a. | Gate valve, UL and FM global approved
a.1 | 150 mm diameter | 6 | Ea | 3686 | 5.4 | 0.6 | 6 | 19904.4 | 2211.6 | 22116 | 100% | 1250 | 100 | 300 | 9900 | 12216
b. | Alarm check valve, UL and FM global approved
b.1 | 150 mm diameter | 3 | Ea | 5577.5 | 2.25 | 0.75 | 3 | 12549.375 | 4183.125 | 16732.5 | 100% | 3830 | 200 | 100 | 12390 | 4342.5
c. | Zone control valve assembly
c.1 | 100 mm diameter | 9 | Ea | 5626 | 8.1 | 0.9 | 9 | 45570.6 | 5063.4 | 50634 | 100% | 3000 | 150 | 100 | 29250 | 21384
2.0 | Fire-Department Connections
Two way, swivel fittings, Dust caps and chains of same material as body, chrome plated finish and threads to match local fire department hardware
a. | Flush wall mounted fire department connection with check valve
a.1 | Two-way swivel fittings, 65 x 65 x 100 mm single clapper Siamese-type connections | 3 | Ea | 4462 | 2.25 | 0.75 | 3 | 10039.5 | 3346.5 | 13386 | 100% | 450 | 150 | 100 | 2100 | 11286
3.0 | Wet-Pipe Sprinkler Systems
a. | Black steel fire water pipes
Supply and installation of black steel pipe seamless type as per ASTM A53 including supports, hangers, fixing, fitting, all other accessories and associated Works as per Contract drawings and specifications.
a.1 | 25 mm diameter | 1305 | m | 53.35 | 1305 | 0 | 1305 | 69621.75 | 0 | 69621.75 | 100% | 15 | 7.5 | 0 | 29362.5 | 40259.25
a.2 | 32 mm diameter | 90 | m | 63.05 | 90 | 0 | 90 | 5674.5 | 0 | 5674.5 | 100% | 20 | 10 | 0 | 2700 | 2974.5
a.3 | 40 mm diameter | 120 | m | 77.6 | 120 | 0 | 120 | 9312 | 0 | 9312 | 100% | 24 | 12 | 0 | 4320 | 4992
a.4 | 50 mm diameter | 60 | m | 95.06 | 60 | 0 | 60 | 5703.6 | 0 | 5703.6 | 100% | 28 | 14 | 0 | 2520 | 3183.6
a.5 | 65 mm diameter | 300 | m | 169.75 | 298.75 | 1.25 | 300 | 50712.8125 | 212.1875 | 50925 | 100% | 30 | 15 | 0 | 13500 | 37425
a.6 | 80 mm diameter | 150 | m | 190.12 | 150 | 0 | 150 | 28518 | 0 | 28518 | 100% | 35 | 25 | 0 | 9000 | 19518
a.7 | 100 mm diameter | 30 | m | 237.65 | 30 | 0 | 30 | 7129.5 | 0 | 7129.5 | 100% | 90 | 60 | 0 | 4500 | 2629.5
a.8 | 150 mm diameter | 90 | m | 344.35 | 89.95 | 0.05 | 90 | 30974.2825 | 17.2175 | 30991.5 | 100% | 170 | 90 | 0 | 23400 | 7591.5
b. | Fire water sprinkler head
Sprinkler Head, UL listed FM approved, chrome-plated, bronze and factory painted; Shall be of one manufacturer. (No mixing of sprinkler brands shall be permitted).
b.1 | Pendent type | 480 | Ea | 63.05 | 479.9999 | 7e-05 | 480 | 30263.9956 | 0.0044135 | 30264 | 100% | 25 | 5 | 100 | 62400 | -32136
b.2 | Upright type | 15 | Ea | 33.95 | 14.9965 | 0.0035 | 15 | 509.1312 | 0.11883 | 509.25 | 100% | 19 | 5 | 100 | 1860 | -1350.75
b.3 | Wall side type | 282 | Ea | 72.75 | 281.9966 | 0.00338 | 282 | 20515.2541 | 0.24589 | 20515.5 | 100% | 59 | 5 | 100 | 46248 | -25732.5
4.0 | Fire-Suppression Standpipes
a. | Fire Hose Cabinet
Supply and installation of Surface mounted fire hose Cabinets Made of Stainless Steel, dimension (W 750 x H 850 x D 180). with Synthetic Single Jacket Hose 1.5” x 30 meter long and (1) multipurpose dry powder Extinguisher include fittings, joints, unions, dielectric fittings, flanges, gaskets, grooved mechanical couplings, nuts and bolts, hangers and supports and labelling.
a.1 | FHC-II | 18 | Ea | 4704.5 | 18 | 0 | 18 | 84681 | 0 | 84681 | 100% | 4200 | 250 | 400 | 87300 | -2619
| SUB-TOTAL ITEM NO. B3-21 00 00 | xxx | xxx |  |  |  |  | 431679.7009 | 15034.3991 | 446714.1 |  |  |  |  | 340750.5 | 105963.6
| (TO BE CARRIED TO COMPOSITE SUMMARY) | 0
| OWNER | CONSULTANT | [5 empty] | CONTRACTOR

## ISOLATE - E
ISOLATE - E
| B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR)
DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative | Percentage | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 28-ELECTRONIC SAFETY AND SECURITY
Fire Detection and Alarm
Fire alarm control panel (FACP)
Supply, installation, testing and commissioning of a microprocessor based, addressable fire alarm control panel, complete with Chassis, 640-Character backlit LCD display, QWERTY programming and control keypad, loop cards, zone and input/output modules, supervisory devices, auxiliary relays, network capability modules, battery, battery charger, printer, internal alarm, interface contacts and all accessories and hardware as shown on the Contract drawings and specified in the Contract documents and to complete the fully functional, operable, reliable and maintainable fire alarm system.
Microprocessor based, addressable FACP, 5 loop type | 1 | Ea | 22795 | 0.9 | 0.1 | 1 | 20515.5 | 2279.5 | 22795 | 100% | 16900 | 80 | 16980 | 5815
Power supply unit, batteries and battery chargers | 1 | Ea | 4365 | 0 | 1 | 1 | 0 | 4365 | 4365 | 100% | 0 | 0 | 0 | 4365
Supply, selection and calculation, installation, testing and commissioning of FACP power supply unit, batteries for at least 24 hours during the normal operations and 15 mins under emergency full loaded condition. Provide separate combination of power Supply and battery enclosure when large batteries are required and not be able embedded inside FACP panel.
Detection and initiation devices
Supply, installation, testing and commissioning of intelligent, addressable type fire alarm detectors and initiating devices as shown on the Contract drawings and specified in the Contract documents complete with all mounting accessories including boxes, connectors and terminations.
Smoke detector - photoelectric, addressable, self diagnostic, self address | 87 | Ea | 339.5 | 78.15 | 8.85 | 87 | 26531.925 | 3004.575 | 29536.5 | 100% | 120 | 80 | 17400 | 12136.5
Heat detector - rate of rise type with fix temperature | 3 | Ea | 339.5 | 8.1 | -5.1 | 3 | 2749.95 | -1731.45 | 1018.5 | 100% | 110 | 80 | 570 | 448.5
Addressable manual fire alarm pull station | 4 | Ea | 291 | 16.2 | -12.2 | 4 | 4714.2 | -3550.2 | 1164 | 100% | 160 | 80 | 960 | 204
Addressable manual fire alarm pull station, weather proof | 0 | Ea | 368.6 | 5.37 | -5.37 | 0 | 1979.382 | -1979.382 | 0 | #DIV/0! | 180 | 80 | 0 | 0
Other initiating devices and control devices
Supply, Installation, testing and commissioning of all conventional I/O interfaces devices for interface and Integration with firefighting systems, gas alarm and control systems, lift safety devices, fire water pumps, HVAC systems. elevators and all other specified equipment as per contract drawings and specifications, complete with all mounting accessories including boxes and terminations.
Fire alarm monitoring module (MM) | 8 | Ea | 436.5 | 21.6 | -13.6 | 8 | 9428.4 | -5936.4 | 3492 | 100% | 140 | 80 | 1760 | 1732
Notification appliances
Supply, installation, testing and commissioning of visual and sound alarm devices as shown on the Contract drawings and specified in the Contract documents complete with all mounting accessories including boxes and terminations.
Bells, indoor with strobe lights / beacons - red body, red lens for fire alarm | 5 | Ea | 388 | 18.86 | -13.86 | 5 | 7317.68 | -5377.68 | 1940 | 100% | 212 | 80 | 1460 | 480
Bells, indoor with strobe lights / beacons - red body, red lens for fire alarm, weather proof | 2 | Ea | 436.5 | 10.8 | -8.8 | 2 | 4714.2 | -3841.2 | 873 | 100% | 250 | 80 | 660 | 213
Fire alarm cables - fire resistant cable, 300V/500V, red sheath with low emission of smoke, halogen free, thermoplastic material |  |  | 0
To include for the procurement, supply, factory testing, delivery to Site, installation, testing and commissioning of the cables, termination materials and all cable support and wiring, identification accessories.
2C x 2.5 mm², Stranded plain copper wire or solid conductor, overall shield with drain wire for SLC loop | 800 | m | 24.25 | 760 | 40 | 800 | 18430 | 970 | 19400 | 100% | 8 | 0 | 6400 | 13000
2C x 2.5 mm², Stranded plain copper wire or solid conductor, overall shield with drain wire for NAC Loop | 400 | m | 24.25 | 380 | 20 | 400 | 9215 | 485 | 9700 | 100% | 8 | 0 | 3200 | 6500
Fire alarm cable conduit, all JB boxes, fittings and accessories for cable installations
To include for the procurement, supply, installation of PVC conduits and flexible metallic conduits for fire cables, junction boxes, fittings, accessories and all other relevant items or Works to complete fully Fire alarm detection system installations.
20 mm diameter, PVC conduits | 0 | m | 24.25 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
SUB-TOTAL ITEM NO. B1-28 00 00 | xxx | xxx |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 49390 | 44894
(TO BE CARRIED TO COMPOSITE SUMMARY) | [6 empty] | 105596.237 | -11312.237 | 94284
OWNER | CONSULTANT | [5 empty] | CONTRACTOR

## ISOLATED-EXT
ISOLATED
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR) |  |  | Percentage
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative |  | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 10 - SPECIALTIES
1.0 | Fire Extinguishers
Includes mounting brackets, fasteners, service tags, fully charged and ready to use extinguishers.
a. | Multipurpose dry chemical type, UL rated ABC
a.1 | FE-1, 6 kg, multi purpose fire extinguisher | 9 | Ea | 243 | 7 | 2 | 9 | 1701 | 486 | 2187 | 100% | 240 | 10 | 2250 | -63
b. | Wet chemical type, UL rated class K
b.1 | FE-3, kitchen type-K fire extinguisher 2 gallon | 2 | Ea | 534 | 1.3 | 0.7 | 2 | 694.2 | 373.8 | 1068 | 100% | 320 | 10 | 660 | 408
c. | Automatic fire extinguisher
c.1 | FE-2, 15 kg, multi purpose fire extinguisher, ceiling mounted | 7 | Ea | 485 | 4.55 | 2.45 | 7 | 2206.75 | 1188.25 | 3395 | 100% | 334 | 10 | 2408 | 987
d. | Fire blanket
Supply and installation of fire blanket of specified type to be located in kitchen with all fittings and supports required to provide satisfactory operation.
d.1 | Fire blanket, standard size (1.2 meter x 1.2 meter), NFPA approved | 2 | Ea | 391 | 2 | 0 | 2 | 782 | 0 | 782 | 100% | 16 | 10 | 52 | 730
| SUB-TOTAL ITEM NO. B6-10 00 00 | xxx | xxx |  |  |  |  | 5383.95 | 2048.05 | 7432 |  |  |  | 5370 | 2062

## ISOLATED
ISOLATED
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR)
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative | Percentage | Actual price | accessories | Actual Labour charge | Total AP+LC | Profit
DIVISION 21 - FIRE SUPPRESSION
1.0 | General-Duty Valves for Water-Based Fire-Suppression Piping
Supply and installation of valves including all fixings, supports, all other accessories and associated Works.
a. | Gate valve, UL and FM global approved
a.1 | 150 mm diameter | 2 | Ea | 3686 | 1.49 | 0.51 | 2 | 5492.14 | 1879.86 | 7372 | 100% | 1250 | 100 | 300 | 3300 | 4072
b. | Alarm check valve, UL and FM global approved
b.1 | 150 mm diameter | 1 | Ea | 5577.5 | 0.75 | 0.25 | 1 | 4183.125 | 1394.375 | 5577.5 | 100% | 3830 | 200 | 100 | 4130 | 1447.5
c. | Zone control valve assembly
c.1 | 100 mm diameter | 2 | Ea | 5626 | 1.5 | 0.5 | 2 | 8439 | 2813 | 11252 | 100% | 3000 | 150 | 100 | 6500 | 4752
2.0 | Fire-Department Connections
Two way, swivel fittings, Dust caps and chains of same material as body, chrome plated finish and threads to match local fire department hardware
a. | Flush wall mounted fire department connection with check valve
a.1 | Two-way swivel fittings, 65 x 65 x 100 mm single clapper Siamese-type connections | 1 | Ea | 4462 | 0.65 | 0.35 | 1 | 2900.3 | 1561.7 | 4462 | 100% | 450 | 150 | 100 | 700 | 3762
3.0 | Wet-Pipe Sprinkler Systems
a. | Black steel fire water pipes
Supply and installation of black steel pipe seamless type as per ASTM A53 including supports, hangers, fixing, fitting, all other accessories and associated Works as per Contract drawings and specifications.
a.1 | 25 mm diameter | 250 | m | 53.35 | 250 | 0 | 250 | 13337.5 | 0 | 13337.5 | 100% | 15 | 7.5 | 0 | 5625 | 7712.5
a.2 | 32 mm diameter | 10 | m | 63.05 | 10 | 0 | 10 | 630.5 | 0 | 630.5 | 100% | 20 | 10 | 0 | 300 | 330.5
a.3 | 40 mm diameter | 40 | m | 77.6 | 40 | 0 | 40 | 3104 | 0 | 3104 | 100% | 24 | 12 | 0 | 1440 | 1664
a.4 | 50 mm diameter | 30 | m | 95.06 | 30 | 0 | 30 | 2851.8 | 0 | 2851.8 | 100% | 28 | 14 | 0 | 1260 | 1591.8
a.5 | 63 mm diameter | 70 | m | 169.75 | 69.925 | 0.075 | 70 | 11869.7687 | 12.7313 | 11882.5 | 100% | 30 | 15 | 0 | 3150 | 8732.5
a.6 | 80 mm diameter | 40 | m | 190.12 | 40 | 0 | 40 | 7604.8 | 0 | 7604.8 | 100% | 35 | 25 | 0 | 2400 | 5204.8
a.7 | 100 mm diameter | 10 | m | 237.65 | 10 | 0 | 10 | 2376.5 | 0 | 2376.5 | 100% | 90 | 60 | 0 | 1500 | 876.5
a.8 | 150 mm diameter | 40 | m | 344.35 | 40.05 | -0.05 | 40 | 13791.2175 | -17.2175 | 13774 | 100% | 170 | 90 | 0 | 10400 | 3374
b. | Fire water sprinkler head | 0
Sprinkler Head, UL listed FM approved, chrome-plated, bronze and factory painted; Shall be of one manufacturer. (No mixing of sprinkler brands shall be permitted).
b.1 | Pendent type | 122 | Ea | 63.05 | 122 | 0 | 122 | 7692.1 | 0 | 7692.1 | 100% | 25 | 5 | 100 | 15860 | -8167.9
b.2 | Upright type | 6 | Ea | 33.95 | 6 | 0 | 6 | 203.7 | 0 | 203.7 | 100% | 19 | 5 | 100 | 744 | -540.3
b.3 | Wall side type | 47 | Ea | 72.75 | 47 | 0 | 47 | 3419.25 | 0 | 3419.25 | 100% | 59 | 5 | 100 | 7708 | -4288.75
4.0 | Fire-Suppression Standpipes
a. | Fire Hose Cabinet
Supply and installation of Surface mounted fire hose Cabinets Made of Stainless Steel, dimension (W 750 x H 850 x D 180). with Synthetic Single Jacket Hose 1.5” x 30 meter long and (1) multipurpose dry powder Extinguisher include fittings, joints, unions, dielectric fittings, flanges, gaskets, grooved mechanical couplings, nuts and bolts, hangers and supports and labelling.
a.1 | FHC-II | 4 | Ea | 4704.5 | 4 | 0 | 4 | 18818 | 0 | 18818 | 100% | 4200 | 250 | 400 | 19400 | -582
| SUB-TOTAL ITEM NO. B6-21 00 00 | xxx | xxx |  |  |  |  | 106713.7013 | 7644.4488 | 114358.15 |  |  |  |  | 84417 | 29941.15
(TO BE CARRIED TO COMPOSITE SUMMARY)
| OWNER | CONSULTANT | [5 empty] | CONTRACTOR

## SENIOR - E
SENIOR - E
|  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR)
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative | Percentage | Actual price | Actual Labour charge | Total AP+LC | Profit
PAY ITEM NO.
DIVISION 28-ELECTRONIC SAFETY AND SECURITY
Supply and installation of IP Fixed cameras, POE+ TCP/IP and IP Indoor fixed mini dome camera-ceiling mounted, including all accessories, testing, commissioning and configuration of the network and other Works as shown on the Contract drawings and specified in the Contract documents.
2.0 | Fire Detection and Alarm
a. | Fire alarm control panel (FACP)
Supply, installation, testing and commissioning of a microprocessor based, addressable fire alarm control panel, complete with Chassis, 640-Character backlit LCD display, QWERTY programming and control keypad, loop cards, zone and input/output modules, supervisory devices, auxiliary relays, network capability modules, battery, battery charger, printer, internal alarm, interface contacts and all accessories and hardware as shown on the Contract drawings and specified in the Contract documents and to complete the fully functional, operable, reliable and maintainable fire alarm system.
a.1 | Microprocessor based, addressable FACP,5 loop type | 3 | Ea | 22795 | 2.7 | 0.3 | 3 | 61546.5 | 6838.5 | 68385 | 100% | 16900 | 80 | 50940 | 17445
b. | Power supply unit, batteries and battery chargers | 3 | Ea | 4365 | 0 | 3 | 3 | 0 | 13095 | 13095 | 100% | 0 | 0 | 0 | 13095
Supply, selection and calculation, installation, testing and commissioning of FACP power supply unit, batteries for at least 24 hours during the normal operations and 15 mins under emergency full loaded condition. Provide separate combination of power Supply and battery enclosure when large batteries are required and not be able embedded inside FACP panel.
c. | Detection and initiation devices
Supply, installation, testing and commissioning of intelligent, addressable type fire alarm detectors and initiating devices as shown on the Contract drawings and specified in the Contract documents complete with all mounting accessories including boxes, connectors and terminations.
c.1 | Smoke detector - photoelectric, addressable, self diagnostic, self address | 474 | Ea | 339.5 | 426.33 | 47.67 | 474 | 144739.035 | 16183.965 | 160923 | 100% | 120 | 80 | 94800 | 66123
c.2 | Heat detector - rate of rise type with fix temperature | 18 | Ea | 291 | 16.25 | 1.75 | 18 | 4728.75 | 509.25 | 5238 | 100% | 110 | 80 | 3420 | 1818
c.3 | Addressable manual fire alarm pull station | 6 | Ea | 368.6 | 5.4 | 0.6 | 6 | 1990.44 | 221.16 | 2211.6 | 100% | 160 | 80 | 1440 | 771.6
c.4 | Addressable manual fire alarm pull station, weather proof
d. | Other initiating devices and control devices
Supply, Installation, testing and commissioning of all conventional I/O interfaces devices for interface and Integration with firefighting systems, gas alarm and control systems, lift safety devices, fire water pumps, HVAC systems. elevators and all other specified equipment as per contract drawings and specifications, complete with all mounting accessories including boxes and terminations.
d.1 | Fire alarm monitoring module (MM) | 24 | Ea | 436.5 | 21.6 | 2.4 | 24 | 9428.4 | 1047.6 | 10476 | 100% | 140 | 80 | 5280 | 5196
e. | Notification appliances
Supply, installation, testing and commissioning of visual and sound alarm devices as shown on the Contract drawings and specified in the Contract documents complete with all mounting accessories including boxes and terminations.
e.1 | Bells, indoor with strobe lights / beacons - red body, red lens for fire alarm | 27 | Ea | 388 | 24.3 | 2.7 | 27 | 9428.4 | 1047.6 | 10476 | 100% | 212 | 80 | 7884 | 2592
e.2 | Bells, indoor with strobe lights / beacons - red body, red lens for fire alarm, weather proof | 12 | Ea | 436.5 | 10.82 | 1.18 | 12 | 4722.93 | 515.07 | 5238 | 100% | 250 | 80 | 3960 | 1278
f. | Fire alarm cables - fire resistant cable, 300V/500V, red sheath with low emission of smoke, halogen free, thermoplastic material
To include for the procurement, supply, factory testing, delivery to Site, installation, testing and commissioning of the cables, termination materials and all cable support and wiring, identification accessories.
f.1 | 2C x 2.5 mm², Stranded plain copper wire or solid conductor, overall shield with drain wire for SLC loop | 3600 | m | 24.25 | 3434 | 166 | 3600 | 83274.5 | 4025.5 | 87300 | 100% | 8 | 0 | 28800 | 58500
f.2 | 2C x 2.5 mm², Stranded plain copper wire or solid conductor, overall shield with drain wire for NAC Loop | 1800 | m | 24.25 | 1717 | 83 | 1800 | 41637.25 | 2012.75 | 43650 | 100% | 8 | 0 | 14400 | 29250
g. | Fire alarm cable conduit, all JB boxes, fittings and accessories for cable installations
To include for the procurement, supply, installation of PVC conduits and flexible metallic conduits for fire cables, junction boxes, fittings, accessories and all other relevant items or Works to complete fully Fire alarm detection system installations.
g.1 | 20 mm diameter, PVC conduits | 0 | m | 24.25 | 0 | 0 | 0 | 0 | 0 | 0
| SUB-TOTAL ITEM NO. B1-28 00 00 | xxx | xxx |  |  |  |  | 361496.205 | 45496.395 | 406992.6 |  |  |  | 210924 | 196068.6
4.0 | (TO BE CARRIED TO COMPOSITE SUMMARY)
a.
| OWNER | CONSULTANT | [5 empty] | CONTRACTOR

## SENIOR-EXT
SENIOR
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR) |  |  | Percentage
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative |  | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 10 - SPECIALTIES
2.0 | Fire Extinguishers
Includes mounting brackets, fasteners, service tags, fully charged and ready to use extinguishers.
a. | Multipurpose dry chemical type, UL rated ABC
a.1 | FE-1, 6 kg, multi purpose fire extinguisher | 42 | Ea | 250 | 32 | 10 | 42 | 8000 | 2500 | 10500 | 100% | 240 | 10 | 10500 | 0
b. | Automatic fire extinguisher
b.1 | FE-3, 15 kg, multi purpose fire extinguisher, ceiling mounted | 12 | Ea | 631 | 12 | 0 | 12 | 7572 | 0 | 7572 | 100% | 334 | 10 | 4128 | 3444
| SUB-TOTAL ITEM NO. B4-10 00 00 | xxx | xxx |  |  |  |  | 15572 | 2500 | 18072 |  |  |  | 14628 | 3444

## SENIOR
SENIOR
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR)
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative | Percentage | Actual price | accessories | Actual Labour charge | Total AP+LC | Profit
DIVISION 21 - FIRE SUPPRESSION
1.0 | General-Duty Valves for Water-Based Fire-Suppression Piping
Supply and installation of valves including all fixings, supports, all other accessories and associated Works.
a. | Gate valve, UL and FM global approved
a.1 | 150 mm diameter | 6 | Ea | 3686 | 5.4 | 0.6 | 6 | 19904.4 | 2211.6 | 22116 | 100% | 1250 | 100 | 300 | 9900 | 12216
b. | Alarm check valve, UL and FM global approved
b.1 | 150 mm diameter | 3 | Ea | 5577.5 | 2.7 | 0.3 | 3 | 15059.25 | 1673.25 | 16732.5 | 100% | 3830 | 200 | 100 | 12390 | 4342.5
c. | Zone control valve assembly
c.1 | 150 mm diameter | 9 | Ea | 5626 | 8.1 | 0.9 | 9 | 45570.6 | 5063.4 | 50634 | 100% | 3000 | 150 | 100 | 29250 | 21384
2.0 | Fire-Department Connections
Two way, swivel fittings, Dust caps and chains of same material as body, chrome plated finish and threads to match local fire department hardware
a. | Flush wall mounted fire department connection with check valve
a.1 | Two-way swivel fittings, 65 x 65 x 100 mm single clapper Siamese-type connections | 3 | Ea | 4462 | 2.7 | 0.3 | 3 | 12047.4 | 1338.6 | 13386 | 100% | 450 | 150 | 100 | 2100 | 11286
3.0 | Wet-Pipe Sprinkler Systems
a. | Black steel fire water pipes
Supply and installation of black steel pipe seamless type as per ASTM A53 including supports, hangers, fixing, fitting, all other accessories and associated Works as per Contract drawings and specifications.
a.1 | 25 mm diameter | 1485 | m | 53.35 | 1491.4417 | -6.4417 | 1485 | 79568.4129 | -343.6629 | 79224.75 | 100% | 15 | 7.5 | 0 | 33412.5 | 45812.25
a.2 | 32 mm diameter | 90 | m | 63.05 | 89.95 | 0.05 | 90 | 5671.3475 | 3.1525 | 5674.5 | 100% | 20 | 10 | 0 | 2700 | 2974.5
a.3 | 40 mm diameter | 135 | m | 77.6 | 134.3833 | 0.61667 | 135 | 10428.1467 | 47.8533 | 10476 | 100% | 24 | 12 | 0 | 4860 | 5616
a.4 | 50 mm diameter | 90 | m | 95.06 | 89.625 | 0.375 | 90 | 8519.7525 | 35.6475 | 8555.4 | 100% | 28 | 14 | 0 | 3780 | 4775.4
a.5 | 65 mm diameter | 345 | m | 169.75 | 343.6167 | 1.3833 | 345 | 58328.9292 | 234.8208 | 58563.75 | 100% | 30 | 15 | 0 | 15525 | 43038.75
a.6 | 80 mm diameter | 180 | m | 190.12 | 179.8667 | 0.13333 | 180 | 34196.2507 | 25.3493 | 34221.6 | 100% | 35 | 25 | 0 | 10800 | 23421.6
a.7 | 100 mm diameter | 30 | m | 237.65 | 30 | 0 | 30 | 7129.5 | 0 | 7129.5 | 100% | 90 | 60 | 0 | 4500 | 2629.5
a.8 | 150 mm diameter | 120 | m | 344.35 | 119.5 | 0.5 | 120 | 41149.825 | 172.175 | 41322 | 100% | 170 | 90 | 0 | 31200 | 10122
b. | Fire water sprinkler head
Sprinkler Head, UL listed FM approved, chrome-plated, bronze and factory painted; Shall be of one manufacturer. (No mixing of sprinkler brands shall be permitted).
b.1 | Pendent type | 546 | Ea | 63.05 | 491.4 | 54.6 | 546 | 30982.77 | 3442.53 | 34425.3 | 100% | 25 | 5 | 100 | 70980 | -36554.7
b.2 | Upright type | 18 | Ea | 33.95 | 16.2 | 1.8 | 18 | 549.99 | 61.11 | 611.1 | 100% | 19 | 5 | 100 | 2232 | -1620.9
b.3 | Wall side type | 336 | Ea | 72.75 | 301.3 | 34.7 | 336 | 21919.575 | 2524.425 | 24444 | 100% | 59 | 5 | 100 | 55104 | -30660
4.0 | Fire-Suppression Standpipes
a. | Fire Hose Cabinet
Supply and installation of Surface mounted fire hose Cabinets Made of Stainless Steel, dimension (W 750 x H 850 x D 180). with Synthetic Single Jacket Hose 1.5” x 30 meter long and (1) multipurpose dry powder Extinguisher include fittings, joints, unions, dielectric fittings, flanges, gaskets, grooved mechanical couplings, nuts and bolts, hangers and supports and labelling.
a.1 | FHC-II | 18 | Ea | 4704.5 | 18 | 0 | 18 | 84681 | 0 | 84681 | 100% | 4200 | 250 | 400 | 87300 | -2619
| SUB-TOTAL ITEM NO. B4-21 00 00 | xxx | xxx |  |  |  |  | 475707.1494 | 16490.2506 | 492197.4 |  |  |  |  | 376033.5 | 116163.9
| (TO BE CARRIED TO COMPOSITE SUMMARY) | 0
| OWNER | CONSULTANT | [5 empty] | CONTRACTOR

## ADMIN -E
ADMIN - E
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR)
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative | Percentage | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 28-ELECTRONIC SAFETY AND SECURITY
2.0 | Fire Detection and Alarm
a. | Fire alarm control panel (FACP)
Supply, installation, testing and commissioning of a microprocessor based, addressable fire alarm control panel, complete with Chassis, 640-Character backlit LCD display, QWERTY programming and control keypad, loop cards, zone and input/output modules, supervisory devices, auxiliary relays, network capability modules, battery, battery charger, printer, internal alarm, interface contacts and all accessories and hardware as shown on the Contract drawings and specified in the Contract documents and to complete the fully functional, operable, reliable and maintainable fire alarm system.
a.1 | Microprocessor based, addressable FACP,5 loop type | 1 | Ea | 22795 | 0.9 | 0.1 | 1 | 20515.5 | 2279.5 | 22795 | 100% | 16900 | 80 | 16980 | 5815
b. | Power supply unit, batteries and battery chargers | 1 | Ea | 4365 | 0 | 1 | 1 | 0 | 4365 | 4365 | 100% | 0 | 0 | 0 | 4365
Supply, selection and calculation, installation, testing and commissioning of FACP power supply unit, batteries for at least 24 hours during the normal operations and 15 mins under emergency full loaded condition. Provide separate combination of power Supply and battery enclosure when large batteries are required and not be able embedded inside FACP panel.
c. | Detection and initiation devices
Supply, installation, testing and commissioning of intelligent, addressable type fire alarm detectors and initiating devices as shown on the Contract drawings and specified in the Contract documents complete with all mounting accessories including boxes, connectors and terminations.
c.1 | Smoke detector - photoelectric, addressable, self diagnostic, self address | 52 | Ea | 339.5 | 46.8 | 5.2 | 52 | 15888.6 | 1765.4 | 17654 | 100% | 120 | 80 | 10400 | 7254
c.2 | Heat detector - rate of rise type with fix temperature | 2 | Ea | 291 | 1.8 | 0.2 | 2 | 523.8 | 58.2 | 582 | 100% | 110 | 80 | 380 | 202
c.3 | Addressable manual fire alarm pull station | 4 | Ea | 368.6 | 3.6 | 0.4 | 4 | 1326.96 | 147.44 | 1474.4 | 100% | 160 | 80 | 960 | 514.4
d. | Other initiating devices and control devices
Supply, Installation, testing and commissioning of all conventional I/O interfaces devices for interface and Integration with firefighting systems, gas alarm and control systems, lift safety devices, fire water pumps, HVAC systems. elevators and all other specified equipment as per contract drawings and specifications, complete with all mounting accessories including boxes and terminations.
d.1 | Fire alarm monitoring module (MM) | 3 | Ea | 436.5 | 2.7 | 0.3 | 3 | 1178.55 | 130.95 | 1309.5 | 100% | 140 | 80 | 660 | 649.5
e. | Notification appliances
Supply, installation, testing and commissioning of visual and sound alarm devices as shown on the Contract drawings and specified in the Contract documents complete with all mounting accessories including boxes and terminations.
e.1 | Bells, indoor with strobe lights / beacons - red body, red lens for fire alarm | 4 | Ea | 388 | 0 | 4 | 4 | 0 | 1552 | 1552 | 100% | 212 | 80 | 1168 | 384
e.2 | Bells, indoor with strobe lights / beacons - red body, red lens for fire alarm, weather proof | 2 | Ea | 436.5 | 0 | 2 | 2 | 0 | 873 | 873 | 100% | 250 | 80 | 660 | 213
f. | Fire alarm cables - fire resistant cable, 300V/500V, red sheath with low emission of smoke, halogen free, thermoplastic material
To include for the procurement, supply, factory testing, delivery to Site, installation, testing and commissioning of the cables, termination materials and all cable support and wiring, identification accessories.
f.1 | 2C x 2.5 mm², Stranded plain copper wire or solid conductor, overall shield with drain wire for SLC loop | 800 | m | 24.25 | 760 | 40 | 800 | 18430 | 970 | 19400 | 100% | 8 | 0 | 6400 | 13000
f.2 | 2C x 2.5 mm², Stranded plain copper wire or solid conductor, overall shield with drain wire for NAC Loop | 400 | m | 24.25 | 380 | 20 | 400 | 9215 | 485 | 9700 | 100% | 8 | 0 | 3200 | 6500
g. | Fire alarm cable conduit, all JB boxes, fittings and accessories for cable installations
To include for the procurement, supply, installation of PVC conduits and flexible metallic conduits for fire cables, junction boxes, fittings, accessories and all other relevant items or Works to complete fully Fire alarm detection system installations.
g.1 | 20 mm diameter, PVC conduits
h. | Fire Alarm Workstations (WS) | 1 | Ea | 63632 | 0 | 1 | 1 | 0 | 63632 | 63632 | 100% | 25800 | 0 | 25800 | 37832
i. | Fire Alarm Fault/Short circuit isolator | 2 | Ea | 1455 | 0 | 2 | 2 | 0 | 2910 | 2910 | 100% | 250 | 0 | 500 | 2410
| SUB-TOTAL ITEM NO. B7-28 00 00 | xxx | xxx |  |  |  |  | 67078.41 | 79168.49 | 146246.9 |  |  |  | 67108 | 79138.9
(TO BE CARRIED TO COMPOSITE SUMMARY)
| OWNER | CONSULTANT | [5 empty] | CONTRACTOR

## ADMIN-EXT
ADMIN
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR) |  |  | Percentage
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative |  | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 10 - SPECIALTIES
1.0 | Fire Extinguishers
Includes mounting brackets, fasteners, service tags, fully charged and ready to use extinguishers.
a. | Multipurpose dry chemical type, UL rated ABC
a.1 | FE-1, 6 kg, multi purpose fire extinguisher | 7 | Ea | 242.5 | 5 | 2 | 7 | 1212.5 | 485 | 1697.5 | 100% | 240 | 10 | 1750 | -52.5
b. | Wet chemical type, UL rated class K |  |  | 0
b.1 | FE-3, kitchen type-K fire extinguisher 2 gallon | 2 | Ea | 533.5 | 1.3 | 0.7 | 2 | 693.55 | 373.45 | 1067 | 100% | 320 | 10 | 660 | 407
c. | Automatic fire extinguisher
c.1 | AFE-3, 15 kg, multi purpose fire extinguisher, ceiling mounted | 1 | Ea | 485 | 0.65 | 0.35 | 1 | 315.25 | 169.75 | 485 | 100% | 334 | 10 | 344 | 141
c.2 | AFE-4, 20 kg, multi purpose fire extinguisher, ceiling mounted | 2 | Ea | 582 | 0 | 2 | 2 | 0 | 1164 | 1164 | 100% | 424 | 10 | 868 | 296
d. | Fire blanket
Supply and installation of fire blanket of specified type to be located in kitchen with all fittings and supports required to provide satisfactory operation.
d.1 | Fire blanket, standard size (1.2 meter x 1.2 meter), NFPA approved | 2 | Ea | 291 | 2 | 0 | 2 | 582 | 0 | 582 | 100% | 16 | 10 | 52 | 530
| SUB-TOTAL ITEM NO. B7-10 00 00 | xxx | xxx |  |  |  |  | 2803.3 | 2192.2 | 4995.5 |  |  |  | 3674 | 1321.5

## ADMIN
ADMIN
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR)
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative | Percentage | Actual price | accessories | Actual Labour charge | Total AP+LC | Profit
DIVISION 21 - FIRE SUPPRESSION
1.0 | Fire-Department Connections
a. | Flush wall mounted fire department connection with check valve
Two way, swivel fittings, Dust caps and chains of same material as body, chrome plated finish and threads to match local fire department hardware
a.1 | Two-way swivel fittings, 65 x 65 x 100 mm single clapper Siamese-type connections | 1 | Ea | 4462 | 0.65 | 0.35 | 1 | 2900.3 | 1561.7 | 4462 | 100% | 450 | 150 | 100 | 700 | 3762
2.0 | Fire-Suppression Standpipes
a. | Fire Hose Cabinet
Supply and installation of Surface mounted fire hose Cabinets Made of Stainless Steel, dimension (W 750 x H 850 x D 180). with Synthetic Single Jacket Hose 1.5” x 30 meter long and (1) multipurpose dry powder Extinguisher include fittings, joints, unions, dielectric fittings, flanges, gaskets, grooved mechanical couplings, nuts and bolts, hangers and supports and labelling.
a.1 | FHC-II | 4 | Ea | 4462 | 4 | 0 | 4 | 17848 | 0 | 17848 | 100% | 4200 | 250 | 400 | 19400 | -1552
3.0 | Wet-Pipe Sprinkler Systems
a. | Black steel fire water pipes
Supply and installation of black steel pipe seamless type as per ASTM A53 including supports, hangers, fixing, fitting, all other accessories and associated Works as per Contract drawings and specifications.
a.1 | 40 mm diameter | 40 | m | 77.6 | 40 | 0 | 40 | 3104 | 0 | 3104 | 100% | 24 | 12 | 0 | 1440 | 1664
a.2 | 50 mm diameter | 30 | m | 95.06 | 30 | 0 | 30 | 2851.8 | 0 | 2851.8 | 100% | 28 | 14 | 0 | 1260 | 1591.8
a.3 | 65 mm diameter | 30 | m | 169.75 | 30 | 0 | 30 | 5092.5 | 0 | 5092.5 | 100% | 30 | 15 | 0 | 1350 | 3742.5
a.4 | 100 mm diameter | 10 | m | 237.65 | 10 | 0 | 10 | 2376.5 | 0 | 2376.5 | 100% | 90 | 60 | 0 | 1500 | 876.5
4.0 | Clean-Agent Fire-Extinguishing Systems
a. | Clean agent modular cylinder with piping, sprinkler heads, nozzles, electric actuator, Instruments Accessories
Piping, fittings, joints, unions, dielectric fittings, flanges, gaskets, grooved mechanical couplings, nuts and bolts, hangers and supports, labeling, discharge manifold - including all piping, valves, controls and support, extinguishing agent containers - including extinguishing agent (less than 999 kg), safety devices and safety brackets, discharge nozzles, control panel (FM approved or UL Listed) - including cylinder cabinets mounting and all wiring, detection devices, graphic annunciator including mounting and all wiring. Testing and commissioning.
a.1 | 28 kg Set | 2 | Ea | 34435 | 1.6 | 0.4 | 2 | 55096 | 13774 | 68870 | 100% | 19000 | 500 | 1500 | 42000 | 26870
a.2 | 56 kg Set | 1 | Ea | 52186 | 0.8 | 0.2 | 1 | 41748.8 | 10437.2 | 52186 | 100% | 30000 | 500 | 1500 | 32000 | 20186
| SUB-TOTAL ITEM NO. B7-21 00 00 | xxx | xxx |  |  |  |  | 131017.9 | 25772.9 | 156790.8 |  |  |  |  | 99650 | 57140.8
(TO BE CARRIED TO COMPOSITE SUMMARY)
| OWNER | CONSULTANT | [6 empty] | CONTRACTOR

## RECREATION - E
REC - E
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR) |  |  | Percentage
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative | Cumulative | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 28-ELECTRONIC SAFETY AND SECURITY
2.0 | Fire Detection and Alarm
a. | Fire alarm control panel (FACP)
Supply, installation, testing and commissioning of a microprocessor based, addressable fire alarm control panel, complete with Chassis, 640-Character backlit LCD display, QWERTY programming and control keypad, loop cards, zone and input/output modules, supervisory devices, auxiliary relays, network capability modules, battery, battery charger, printer, internal alarm, interface contacts and all accessories and hardware as shown on the Contract drawings and specified in the Contract documents and to complete the fully functional, operable, reliable and maintainable fire alarm system.
a.1 | Microprocessor based, addressable FACP, 5 loop type | 1 | Ea | 22795 | 0.9 | 0.1 | 1 | 20515.5 | 2279.5 | 22795 | 100% | 16900 | 80 | 16980 | 5815
b. | Power supply unit, batteries and battery chargers | 1 | Ea | 4365 | 0 | 1 | 1 | 0 | 4365 | 4365 | 100% | 0 | 0 | 0 | 4365
Supply, selection and calculation, installation, testing and commissioning of FACP power supply unit, batteries for at least 24 hours during the normal operations and 15 mins under emergency full loaded condition. Provide separate combination of power Supply and battery enclosure when large batteries are required and not be able embedded inside FACP panel.
c. | Detection and initiation devices
Supply, installation, testing and commissioning of intelligent, addressable type fire alarm detectors and initiating devices as shown on the Contract drawings and specified in the Contract documents complete with all mounting accessories including boxes, connectors and terminations.
c.1 | Smoke detector - photoelectric, addressable, self diagnostic, self address | 99 | Ea | 339.5 | 89.52 | 9.48 | 99 | 30392.04 | 3218.46 | 33610.5 | 100% | 120 | 80 | 19800 | 13810.5
c.2 | Air duct smoke detectors with remote LED indicator and test devices | 14 | Ea | 1746 | 12.6 | 1.4 | 14 | 21999.6 | 2444.4 | 24444 | 100% | 250 | 80 | 4620 | 19824
c.3 | Heat detector - rate of rise type with fix temperature | 2 | Ea | 339.5 | 1.8 | 0.2 | 2 | 611.1 | 67.9 | 679 | 100% | 110 | 80 | 380 | 299
c.4 | Beam detector transmitter, 50 meter range | 2 | Ea | 2783.9 | 1.3 | 0.7 | 2 | 3619.07 | 1948.73 | 5567.8 | 100% | 180 | 80 | 520 | 5047.8
c.5 | Beam detector receiver, 50 meter range | 2 | Ea | 2783.9 | 1.3 | 0.7 | 2 | 3619.07 | 1948.73 | 5567.8 | 100% | 180 | 80 | 520 | 5047.8
c.6 | Addressable manual fire alarm pull station | 12 | Ea | 291 | 10.82 | 1.18 | 12 | 3148.62 | 343.38 | 3492 | 100% | 160 | 80 | 2880 | 612
d. | Other initiating devices and control devices
Supply, Installation, testing and commissioning of all conventional I/O interfaces devices for interface and Integration with firefighting systems, gas alarm and control systems, lift safety devices, fire water pumps, HVAC systems. elevators and all other specified equipment as per contract drawings and specifications, complete with all mounting accessories including boxes and terminations.
d.1 | Fire alarm monitoring module (MM) | 6 | Ea | 436.5 | 5.4 | 0.6 | 6 | 2357.1 | 261.9 | 2619 | 100% | 140 | 80 | 1320 | 1299
e. | Notification appliances
Supply, installation, testing and commissioning of visual and sound alarm devices as shown on the Contract drawings and specified in the Contract documents complete with all mounting accessories including boxes and terminations.
e.1 | Bells, indoor with strobe lights / beacons - red body, red lens for fire alarm | 12 | Ea | 388 | 3.9 | 8.1 | 12 | 1513.2 | 3142.8 | 4656 | 100% | 212 | 80 | 3504 | 1152
e.2 | Bells, indoor with strobe lights / beacons - red body, red lens for fire alarm, weather proof | 4 | Ea | 436.5 | 0 | 4 | 4 | 0 | 1746 | 1746 | 100% | 250 | 80 | 1320 | 426
f. | Fire alarm cables - fire resistant cable, 300V/500V, red sheath with low emission of smoke, halogen free, thermoplastic material
To include for the procurement, supply, factory testing, delivery to Site, installation, testing and commissioning of the cables, termination materials and all cable support and wiring, identification accessories.
f.1 | 2C x 2.5 mm², Stranded plain copper wire or solid conductor, overall shield with drain wire for SLC loop | 2000 | m | 24.25 | 1900 | 100 | 2000 | 46075 | 2425 | 48500 | 100% | 8 | 0 | 16000 | 32500
f.2 | 2C x 2.5 mm², Stranded plain copper wire or solid conductor, overall shield with drain wire for NAC Loop | 800 | m | 24.25 | 760 | 40 | 800 | 18430 | 970 | 19400 | 100% | 8 | 0 | 6400 | 13000
g. | Fire alarm cable conduit, all JB boxes, fittings and accessories for cable installations
To include for the procurement, supply, installation of PVC conduits and flexible metallic conduits for fire cables, junction boxes, fittings, accessories and all other relevant items or Works to complete fully Fire alarm detection system installations.
g.1 | 20 mm diameter, PVC conduits | 0 | m | 24.25 | 0 | 0 | 0 | 0 | 0 | 0
| SUB-TOTAL ITEM NO. B8-28 00 00 | xxx | xxx |  | 0 | 0 | 0 | 131764.8 | 18517.3 | 150282.1 |  |  |  | 57264 | 93018.1
(TO BE CARRIED TO COMPOSITE SUMMARY)
| OWNER | CONSULTANT | [5 empty] | CONTRACTOR

## RECREATION-EXT
RECREATION
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR) |  |  | Percentage
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative |  | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 10 - SPECIALTIES
3.0 | Fire Extinguishers
Includes mounting brackets, fasteners, service tags, fully charged and ready to use extinguishers.
a. | Multipurpose dry chemical type, UL rated ABC
a.1 | FE-1, 6 kg, multi purpose fire extinguisher | 39 | Ea | 250 | 29 | 10 | 39 | 7250 | 2500 | 9750 | 100% | 240 | 10 | 9750 | 0
b. | Carbon dioxide type, UL rated BC
b.1 | FE-2, 6kg, carbon dioxide portable fire extinguisher | 2 | Ea | 550 | 1.3 | 0.7 | 2 | 715 | 385 | 1100 | 100% | 500 | 10 | 1020 | 80
c. | Automatic fire extinguisher
c.1 | FE-3, 15 kg, multi purpose fire extinguisher, ceiling mounted | 8 | Ea | 500 | 5.2 | 2.8 | 8 | 2600 | 1400 | 4000 | 100% | 334 | 10 | 2752 | 1248
| SUB-TOTAL ITEM NO. B8-10 00 00 | xxx | xxx |  |  |  |  | 10565 | 4285 | 14850 |  |  |  | 13522 | 1328

## RECREATION
REC
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR)
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative | Percentage | Actual price | accessories | Actual Labour charge | Total AP+LC | Profit
DIVISION 21 - FIRE SUPPRESSION
1.0 | General-Duty Valves for Water-Based Fire-Suppression Piping
Supply and installation of valves including all fixings, supports, all other accessories and associated Works.
a. | Gate valve, UL and FM global approved
a.1 | 150 mm diameter | 2 | Ea | 3686 | 1.8 | 0.2 | 2 | 6634.8 | 737.2 | 7372 | 100% | 1250 | 100 | 300 | 3300 | 4072
b. | Alarm check valve, UL and FM global approved
b.1 | 150 mm diameter | 1 | Ea | 5577.5 | 0.9 | 0.1 | 1 | 5019.75 | 557.75 | 5577.5 | 100% | 3830 | 200 | 100 | 4130 | 1447.5
c. | Zone control valve assembly
c.1 | 100 mm diameter | 2 | Ea | 5626 | 1.79 | 0.21 | 2 | 10070.54 | 1181.46 | 11252 | 100% | 3000 | 150 | 100 | 6500 | 4752
2.0 | Fire-Department Connections
Two way, swivel fittings, Dust caps and chains of same material as body, chrome plated finish and threads to match local fire department hardware
a. | Flush wall mounted fire department connection with check valve
a.1 | Two-way swivel fittings, 65 x 65 x 100 mm single clapper Siamese-type connections | 1 | Ea | 4462 | 0.65 | 0.35 | 1 | 2900.3 | 1561.7 | 4462 | 100% | 450 | 150 | 100 | 700 | 3762
3.0 | Wet-Pipe Sprinkler Systems
a. | Black steel fire water pipes
Supply and installation of black steel pipe seamless type as per ASTM A53 including supports, hangers, fixing, fitting, all other accessories and associated Works as per Contract drawings and specifications.
a.1 | 25 mm diameter | 1080 | m | 53.35 | 972 | 108 | 1080 | 51856.2 | 5761.8 | 57618 | 100% | 15 | 7.5 | 0 | 24300 | 33318
a.2 | 32 mm diameter | 325 | m | 63.05 | 292.5 | 32.5 | 325 | 18442.125 | 2049.125 | 20491.25 | 100% | 20 | 10 | 0 | 9750 | 10741.25
a.3 | 40 mm diameter | 130 | m | 77.6 | 117 | 13 | 130 | 9079.2 | 1008.8 | 10088 | 100% | 24 | 12 | 0 | 4680 | 5408
a.4 | 50 mm diameter | 60 | m | 95.06 | 54 | 6 | 60 | 5133.24 | 570.36 | 5703.6 | 100% | 28 | 14 | 0 | 2520 | 3183.6
a.5 | 65 mm diameter | 130 | m | 169.75 | 117 | 13 | 130 | 19860.75 | 2206.75 | 22067.5 | 100% | 30 | 15 | 0 | 5850 | 16217.5
a.6 | 80 mm diameter | 40 | m | 190.12 | 36 | 4 | 40 | 6844.32 | 760.48 | 7604.8 | 100% | 35 | 25 | 0 | 2400 | 5204.8
a.7 | 100 mm diameter | 80 | m | 237.65 | 72 | 8 | 80 | 17110.8 | 1901.2 | 19012 | 100% | 90 | 60 | 0 | 12000 | 7012
a.8 | 150 mm diameter | 20 | m | 344.35 | 18.025 | 1.975 | 20 | 6206.9087 | 680.0913 | 6887 | 100% | 170 | 90 | 0 | 5200 | 1687
b. | Fire water sprinkler head
Sprinkler Head, UL listed FM approved, chrome-plated, bronze and factory painted; Shall be of one manufacturer. (No mixing of sprinkler brands shall be permitted).
b.1 | Pendent type (K=5.60) | 212 | Ea | 63.05 | 169.6 | 42.4 | 212 | 10693.28 | 2673.32 | 13366.6 | 100% | 25 | 5 | 100 | 27560 | -14193.4
b.2 | Upright type (K=5.60) | 70 | Ea | 33.95 | 56 | 14 | 70 | 1901.2 | 475.3 | 2376.5 | 100% | 19 | 5 | 100 | 8680 | -6303.5
b.3 | Upright type (K=8.0) | 36 | Ea | 72.75 | 23.4 | 12.6 | 36 | 1702.35 | 916.65 | 2619 | 100% | 59 | 5 | 100 | 5904 | -3285
b.4 | Wall side type (K=5.6) | 7 | Ea | 145.5 | 5.6 | 1.4 | 7 | 814.8 | 203.7 | 1018.5 | 100%
4.0 | Fire-Suppression Standpipes
a. | Fire Hose Cabinet
Supply and installation of Surface mounted fire hose Cabinets Made of Stainless Steel, dimension (W 750 x H 850 x D 180). with Synthetic Single Jacket Hose 1.5” x 30 meter long and (1) multipurpose dry powder Extinguisher include fittings, joints, unions, dielectric fittings, flanges, gaskets, grooved mechanical couplings, nuts and bolts, hangers and supports and labelling.
a.1 | FHC-II | 8 | Ea | 4704.5 | 5.2 | 2.8 | 8 | 24463.4 | 13172.6 | 37636 | 100% | 4200 | 250 | 400 | 38800 | -1164
[8 empty] | 198733.9637 | 36418.2863 | 235152.25 |  |  |  |  | 162274 | 71859.75
| SUB-TOTAL ITEM NO. B8-21 00 00 | xxx | xxx
(TO BE CARRIED TO COMPOSITE SUMMARY)
| OWNER | CONSULTANT | [5 empty] | CONTRACTOR

## SERVICE - E
SERVICE - E
|  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR)
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative | Percentage | Actual price | Actual Labour charge | Total AP+LC | Profit
PAY ITEM NO.
DIVISION 28-ELECTRONIC SAFETY AND SECURITY
2.0 | Fire Detection and Alarm
a. | Fire alarm control panel (FACP)
Supply, installation, testing and commissioning of a microprocessor based, addressable fire alarm control panel, complete with Chassis, 640-Character backlit LCD display, QWERTY programming and control keypad, loop cards, zone and input/output modules, supervisory devices, auxiliary relays, network capability modules, battery, battery charger, printer, internal alarm, interface contacts and all accessories and hardware as shown on the Contract drawings and specified in the Contract documents and to complete the fully functional, operable, reliable and maintainable fire alarm system.
a.1 | Microprocessor based, addressable FACP, 5 loop type | 2 | Ea | 22795 | 1.3 | 0.7 | 2 | 29633.5 | 15956.5 | 45590 | 100% | 16900 | 80 | 33960 | 11630
b. | Power supply unit, batteries and battery chargers | 2 | Ea | 4365 | 0 | 2 | 2 | 0 | 8730 | 8730 | 100% | 0 | 0 | 0 | 8730
Supply, selection and calculation, installation, testing and commissioning of FACP power supply unit, batteries for at least 24 hours during the normal operations and 15 mins under emergency full loaded condition. Provide separate combination of power Supply and battery enclosure when large batteries are required and not be able embedded inside FACP panel.
c. | Detection and initiation devices
Supply, installation, testing and commissioning of intelligent, addressable type fire alarm detectors and initiating devices as shown on the Contract drawings and specified in the Contract documents complete with all mounting accessories including boxes, connectors and terminations.
c.1 | Smoke detector - photoelectric, addressable, self diagnostic, self address | 229 | Ea | 339.5 | 148.85 | 80.15 | 229 | 50534.575 | 27210.925 | 77745.5 | 100% | 120 | 80 | 45800 | 31945.5
c.2 | Air duct smoke detectors with remote LED indicator and test devices | 28 | Ea | 1746 | 10.4 | 17.6 | 28 | 18158.4 | 30729.6 | 48888 | 100% | 250 | 80 | 9240 | 39648
c.3 | Heat detector - rate of rise type with fix temperature | 24 | Ea | 339.5 | 8.45 | 15.55 | 24 | 2868.775 | 5279.225 | 8148 | 100% | 110 | 80 | 4560 | 3588
c.4 | Addressable manual fire alarm pull station | 26 | Ea | 291 | 16.9 | 9.1 | 26 | 4917.9 | 2648.1 | 7566 | 100% | 180 | 80 | 6760 | 806
c.5 | Addressable manual fire alarm pull station, weather proof | 5 | Ea | 339.5 | 3.25 | 1.75 | 5 | 1103.375 | 594.125 | 1697.5 | 100% | 250 | 80 | 1650 | 47.5
d. | Other initiating devices and control devices
Supply, Installation, testing and commissioning of all conventional I/O interfaces devices for interface and Integration with firefighting systems, gas alarm and control systems, lift safety devices, fire water pumps, HVAC systems. elevators and all other specified equipment as per contract drawings and specifications, complete with all mounting accessories including boxes and terminations.
d.1 | Fire alarm monitoring module (MM) | 24 | Ea | 436.5 | 15.6 | 8.4 | 24 | 6809.4 | 3666.6 | 10476 | 100% | 140 | 80 | 5280 | 5196
e. | Notification appliances
Supply, installation, testing and commissioning of visual and sound alarm devices as shown on the Contract drawings and specified in the Contract documents complete with all mounting accessories including boxes and terminations.
e.1 | Bells, indoor with strobe lights / beacons - red body, red lens for fire alarm | 28 | Ea | 388 | 18.2 | 9.8 | 28 | 7061.6 | 3802.4 | 10864 | 100% | 212 | 80 | 8176 | 2688
e.2 | Bells, indoor with strobe lights / beacons - red body, red lens for fire alarm, weather proof | 23 | Ea | 436.5 | 14.3 | 8.7 | 23 | 6241.95 | 3797.55 | 10039.5 | 100% | 250 | 80 | 7590 | 2449.5
f. | Fire alarm cables - fire resistant cable, 300V/500V, red sheath with low emission of smoke, halogen free, thermoplastic material
To include for the procurement, supply, factory testing, delivery to Site, installation, testing and commissioning of the cables, termination materials and all cable support and wiring, identification accessories.
f.1 | 2C x 2.5 mm², Stranded plain copper wire or solid conductor, overall shield with drain wire for SLC loop | 2000 | m | 24.25 | 1788 | 212 | 2000 | 43359 | 5141 | 48500 | 100% | 8 | 0 | 16000 | 32500
f.2 | 2C x 2.5 mm², Stranded plain copper wire or solid conductor, overall shield with drain wire for NAC Loop | 800 | m | 24.25 | 712 | 88 | 800 | 17266 | 2134 | 19400 | 100% | 8 | 0 | 6400 | 13000
g. | Fire alarm cable conduit, all JB boxes, fittings and accessories for cable installations
| To include for the procurement, supply, installation of PVC conduits and flexible metallic conduits for fire cables, junction boxes, fittings, accessories and all other relevant items or Works to complete fully Fire alarm detection system installations. | [12 empty] | 145416 | 152228.5
g.1 | 20 mm diameter, PVC conduits | 0 | m | 24.25 | 0 | 0 | 0 | 0 | 0 | 0
| SUB-TOTAL ITEM NO. B9-28 00 00 | xxx | xxx |  |  |  |  | 187954.475 | 109690.025 | 297644.5
(TO BE CARRIED TO COMPOSITE SUMMARY)
| OWNER | CONSULTANT | [5 empty] | CONTRACTOR

## SERVICE-EXT
SERVICE
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR) |  |  | Percentage
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative |  | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 10 - SPECIALTIES
3.0 | Fire Extinguishers
Includes mounting brackets, fasteners, service tags, fully charged and ready to use extinguishers.
a. | Multipurpose dry chemical type, UL rated ABC
a.1 | FE-1, 6 kg, multi purpose fire extinguisher | 102 | Ea | 250 | 77 | 25 | 102 | 19250 | 6250 | 25500 | 100% | 240 | 10 | 25500 | 0
b. | Carbon dioxide type, UL rated BC
b.1 | FE-2, 6kg, carbon dioxide portable fire extinguisher | 7 | Ea | 350 | 4.55 | 2.45 | 7 | 1592.5 | 857.5 | 2450 | 100% | 500 | 10 | 3570 | -1120
c. | Wet chemical type, UL rated class K
c.1 | FE-3, kitchen type-K fire extinguisher 2 gallon | 2 | Ea | 500 | 1.3 | 0.7 | 2 | 650 | 350 | 1000 | 100% | 320 | 10 | 660 | 340
d. | Automatic fire extinguisher
d.1 | AFE-3, 15 kg, multi purpose fire extinguisher, ceiling mounted | 13 | Ea | 500 | 0 | 13 | 13 | 0 | 6500 | 6500 | 100% | 334 | 10 | 4472 | 2028
e. | Fire blanket
Supply and installation of fire blanket of specified type to be located in kitchen with all fittings and supports required to provide satisfactory operation.
e.1 | Fire blanket, standard size (1.2 meter x 1.2 meter), NFPA approved | 2 | Ea | 300 | 0 | 2 | 2 | 0 | 600 | 600 | 100% | 16 | 10 | 52 | 548
| SUB-TOTAL ITEM NO. B9-10 00 00 | xxx | xxx |  |  |  |  | 21492.5 | 14557.5 | 36050 |  |  |  | 34254 | 1796

## SERVICE
SERVICE
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR)
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative | Percentage | Actual price | accessories | Actual Labour charge | Total AP+LC | Profit
DIVISION 21 - FIRE SUPPRESSION
1.0 | General-Duty Valves for Water-Based Fire-Suppression Piping
Supply and installation of valves including all fixings, supports, all other accessories and associated Works.
a. | Gate valve, UL and FM global approved
a.1 | 150 mm diameter | 2 | Ea | 3800 | 1.3 | 0.7 | 2 | 4940 | 2660 | 7600 | 100% | 1250 | 100 | 300 | 3300 | 4300
b. | Alarm check valve, UL and FM global approved
b.1 | 150 mm diameter | 4 | Ea | 5750 | 2.6 | 1.4 | 4 | 14950 | 8050 | 23000 | 100% | 3830 | 200 | 100 | 16520 | 6480
c. | Zone control valve assembly
c.1 | 100 mm diameter | 8 | Ea | 5800 | 5.16 | 2.84 | 8 | 29928 | 16472 | 46400 | 100% | 3000 | 150 | 100 | 26000 | 20400
2.0 | Fire-Department Connections
Two way, swivel fittings, Dust caps and chains of same material as body, chrome plated finish and threads to match local fire department hardware
a. | Flush wall mounted fire department connection with check valve
a.1 | Two-way swivel fittings, 65 x 65 x 100 mm single clapper Siamese-type connections | 4 | Ea | 4600 | 2.6 | 1.4 | 4 | 11960 | 6440 | 18400 | 100% | 450 | 150 | 100 | 2800 | 15600
3.0 | Wet-Pipe Sprinkler Systems
a. | Black steel fire water pipes
Supply and installation of black steel pipe seamless type as per ASTM A53 including supports, hangers, fixing, fitting, all other accessories and associated Works as per Contract drawings and specifications.
a.1 | 25 mm diameter | 2100 | m | 53.35 | 1779.75 | 320.25 | 2100 | 94949.6625 | 17085.3375 | 112035 | 100% | 15 | 7.5 | 0 | 47250 | 64785
a.2 | 32 mm diameter | 535 | m | 63.05 | 453.4125 | 81.5875 | 535 | 28587.6581 | 5144.0919 | 33731.75 | 100% | 20 | 10 | 0 | 16050 | 17681.75
a.3 | 40 mm diameter | 285 | m | 77.6 | 241.5375 | 43.4625 | 285 | 18743.31 | 3372.69 | 22116 | 100% | 24 | 12 | 0 | 10260 | 11856
a.4 | 50 mm diameter | 110 | m | 95.06 | 93.225 | 16.775 | 110 | 8861.9685 | 1594.6315 | 10456.6 | 100% | 28 | 14 | 0 | 4620 | 5836.6
a.5 | 65 mm diameter | 130 | m | 169.75 | 110.175 | 19.825 | 130 | 18702.2062 | 3365.2938 | 22067.5 | 100% | 30 | 15 | 0 | 5850 | 16217.5
a.6 | 80 mm diameter | 200 | m | 190.12 | 169.5 | 30.5 | 200 | 32225.34 | 5798.66 | 38024 | 100% | 35 | 25 | 0 | 12000 | 26024
a.7 | 100 mm diameter | 180 | m | 237.65 | 152.55 | 27.45 | 180 | 36253.5075 | 6523.4925 | 42777 | 100% | 90 | 60 | 0 | 27000 | 15777
a.8 | 150 mm diameter | 40 | m | 344.35 | 33.95 | 6.05 | 40 | 11690.6825 | 2083.3175 | 13774 | 100% | 170 | 90 | 0 | 10400 | 3374
b. | Fire water sprinkler head
Sprinkler Head, UL listed FM approved, chrome-plated, bronze and factory painted; Shall be of one manufacturer. (No mixing of sprinkler brands shall be permitted).
b.1 | Pendent type | 644 | Ea | 65 | 396.78 | 247.22 | 644 | 25790.7 | 16069.3 | 41860 | 100% | 25 | 5 | 100 | 83720 | -41860
b.2 | Upright type | 209 | Ea | 35 | 95.88 | 113.12 | 209 | 3355.8 | 3959.2 | 7315 | 100% | 19 | 5 | 100 | 25916 | -18601
b.3 | Wall side type | 26 | Ea | 75 | 19.175 | 6.825 | 26 | 1438.125 | 511.875 | 1950 | 100% | 59 | 5 | 100 | 4264 | -2314
b.4 | Pendent type for kitchen and laundry | 35 | Ea | 80 | 22.75 | 12.25 | 35 | 1820 | 980 | 2800 | 100%
4.0 | Wet-Chemical Fire-Extinguishing System
Supply and installation Wet-chemical fire-extinguishing piping include Piping, fittings, joints, unions, dielectric fittings, flanges, gaskets, grooved mechanical couplings, nuts and bolts, hangers and supports, labelling; discharge manifold - including all piping, valves, controls and support; extinguishing agent containers - including extinguishing agent safety devices and safety brackets, discharge nozzles, control panel (FM approved or UL Listed) - including mounting and all wiring, detection devices.
a.1 | Wet-chemical fire-extinguishing system | 7 | Set | 18500 | 0 | 7 | 7 | 0 | 129500 | 129500 | 100% | 0 |  |  | 0 | 129500
a.2 | Wet-chemical fire-extinguishing piping | 7 | Set | 2500 | 0 | 7 | 7 | 0 | 17500 | 17500 | 100% | 0 |  |  | 0 | 17500
a.3 | Wet-chemical fire-extinguishing equipment | 7 | Set | 4000 | 0 | 7 | 7 | 0 | 28000 | 28000 | 100% | 0 |  |  | 0 | 28000
4.0 | Fire-Suppression Standpipes
a. | Fire Hose Cabinet
Supply and installation of Surface mounted fire hose Cabinets Made of Stainless Steel, dimension (W 750 x H 850 x D 180). with Synthetic Single Jacket Hose 1.5” x 30 meter long and (1) multipurpose dry powder Extinguisher include fittings, joints, unions, dielectric fittings, flanges, gaskets, grooved mechanical couplings, nuts and bolts, hangers and supports and labelling.
a.1 | FHC-II | 24 | Ea | 4850 | 17.39 | 6.61 | 24 | 84341.5 | 32058.5 | 116400 | 100% | 4200 | 250 | 400 | 116400 | 0
| SUB-TOTAL ITEM NO. B9-21 00 00 | xxx | xxx |  |  |  |  | 428538.4604 | 307168.3896 | 735706.85 |  |  |  |  | 412350 | 320556.85
(TO BE CARRIED TO COMPOSITE SUMMARY)
| OWNER | CONSULTANT | [5 empty] | CONTRACTOR

## PUMP RM-1
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR) |  |  | Percentage
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | UNIT PRICE(SR) -10% ADVANCE PAYMENT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative |  | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 28-ELECTRONIC SAFETY AND SECURITY
2.0 | Fire Detection and Alarm
a. | Detection and initiation devices
Supply, installation, testing and commissioning of intelligent, addressable type fire alarm detectors and initiating devices as shown on the Contract drawings and specified in the Contract documents complete with all mounting accessories including boxes, connectors and terminations.
a.1 | Smoke detector - photoelectric, addressable, self diagnostic, self address, weather proof | 2 | Ea | 339.5 | 305.55 | 0 | 2 | 2 | 0 | 679 | 679 | 100% | 120 | 80 | 400 | 279
a.2 | Addressable manual fire alarm pull station, weather proof | 1 | Ea | 291 | 261.9 | 0 | 1 | 1 | 0 | 291 | 291 | 100% | 160 | 80 | 240 | 51
b. | Fire alarm cables - fire resistant cable, 300V/500V, red sheath with low emission of smoke, halogen free, thermoplastic material |  |  | 0
To include for the procurement, supply, factory testing, delivery to Site, installation, testing and commissioning of the cables, termination materials and all cable support and wiring, identification accessories.
b.1 | 2C x 2.5 mm², Stranded plain copper wire or solid conductor, overall shield with drain wire for NAC Loop | 80 | m | 24.25 | 21.825 | 0 | 80 | 80 | 0 | 1940 | 1940 | 100% | 8 | 0 | 640 | 1300
c. | Fire alarm cable conduit, all JB boxes, fittings and accessories for cable installations
To include for the procurement, supply, installation of PVC conduits and flexible metallic conduits for fire cables, junction boxes, fittings, accessories and all other relevant items or Works to complete fully Fire alarm detection system installations.
c.1 | 20 mm diameter, PVC conduits | 0 | m | 24.25 | 21.825 | 0 | 0 | 0 | 0 | 0 | 0
| SUB-TOTAL ITEM NO. B11-28 00 00 | xxx | xxx | [5 empty] | 0 | 2910 | 2910 |  |  |  | 1280 | 1630
(TO BE CARRIED TO COMPOSITE SUMMARY)
| OWNER | CONSULTANT | [6 empty] | CONTRACTOR

## PUMP-R1-EXT
PUMP01
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR) |  |  | Percentage
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative |  | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 10 - SPECIALTIES
1.0 | Fire Extinguishers
a. | Multipurpose dry chemical type, UL rated ABC
Includes mounting brackets, fasteners, service tags, fully charged and ready to use extinguishers.
a.1 | FE-1, 6 kg, Multi-purpose fire extinguisher | 1 | Ea | 242.5 | 0.75 | 0.25 | 1 | 181.875 | 60.625 | 242.5 | 100% | 240 | 10 | 250 | -7.5
a.2 | FE-2, 6 kg, carbon dioxide fire extinguisher | 1 | Ea | 388 | 0.65 | 0.35 | 1 | 252.2 | 135.8 | 388 | 100% | 500 | 10 | 510 | -122
b. | Automatic fire extinguisher
b.1 | AFE-5, 30 kg, multi purpose fire extinguisher, ceiling mounted | 25 | Ea | 630.5 | 8.45 | 16.55 | 25 | 5327.725 | 10434.775 | 15762.5 | 100% | 435 | 10 | 11125 | 4637.5
| SUB-TOTAL ITEM NO. B11-10 00 00 | xxx | xxx |  |  |  |  | 5761.8 | 10631.2 | 16393 |  |  |  | 11885 | 4508

## PUMP RM-2
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR) |  |  | Percentage
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | UNIT PRICE(SR) -10% ADVANCE PAYMENT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative |  | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 28-ELECTRONIC SAFETY AND SECURITY
2.0 | Fire Detection and Alarm
a. | Detection and initiation devices
Supply, installation, testing and commissioning of intelligent, addressable type fire alarm detectors and initiating devices as shown on the Contract drawings and specified in the Contract documents complete with all mounting accessories including boxes, connectors and terminations.
a.1 | Smoke detector - photoelectric, addressable, self diagnostic, self address, weather proof | 2 | Ea | 339.5 | 305.55 | 0 | 2 | 2 | 0 | 679 | 679 | 100% | 120 | 80 | 400 | 279
a.2 | Addressable manual fire alarm pull station, weather proof | 1 | Ea | 291 | 261.9 | 0 | 1 | 1 | 0 | 291 | 291 | 100% | 160 | 80 | 240 | 51
b. | Other initiating devices and control devices
Supply, Installation, testing and commissioning of all conventional I/O interfaces devices for interface and Integration with firefighting systems, gas alarm and control systems, lift safety devices, fire water pumps, HVAC systems. elevators and all other specified equipment as per contract drawings and specifications, complete with all mounting accessories including boxes and terminations.
b.1 | Fire alarm monitoring module (MM) | 2 | Ea | 4365 | 3928.5 | 0 | 2 | 2 | 0 | 8730 | 8730 | 100% | 140 | 0 | 280 | 8450
c. | Fire alarm cables - fire resistant cable, 300V/500V, red sheath with low emission of smoke, halogen free, thermoplastic material
To include for the procurement, supply, factory testing, delivery to Site, installation, testing and commissioning of the cables, termination materials and all cable support and wiring, identification accessories.
c.1 | 2C x 2.5 mm², Stranded plain copper wire or solid conductor, overall shield with drain wire for NAC Loop | 80 | m | 24.25 | 21.825 | 0 | 80 | 80 | 0 | 1940 | 1940 | 100% | 8 | 0 | 640 | 1300
d. | Fire alarm cable conduit, all JB boxes, fittings and accessories for cable installations
To include for the procurement, supply, installation of PVC conduits and flexible metallic conduits for fire cables, junction boxes, fittings, accessories and all other relevant items or Works to complete fully Fire alarm detection system installations.
d.1 | 20 mm diameter, PVC conduits | 0 | m | 24.25 | 21.825 | 0 | 0 | 0 | 0 | 0 | 0
| SUB-TOTAL ITEM NO. B12-28 00 00 | xxx | xxx |  |  | 0 |  |  | 0 | 11640 | 11640 |  |  |  | 1560 | 10080
(TO BE CARRIED TO COMPOSITE SUMMARY)
| OWNER | CONSULTANT | [6 empty] | CONTRACTOR

## PUMP-R2-EXT
PUMP02
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR) |  |  | Percentage
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative |  | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 10 - SPECIALTIES
1.0 | Fire Extinguishers
Includes mounting brackets, fasteners, service tags, fully charged and ready to use extinguishers.
a. | Multipurpose dry chemical type, UL rated ABC
a.1 | FE-1, 6 kg, multi purpose fire extinguisher | 1 | Ea | 242.5 | 0.75 | 0.25 | 1 | 181.875 | 60.625 | 242.5 | 100% | 240 | 10 | 250 | -7.5
b. | Automatic fire extinguisher
b.1 | FE-2, 6 kg, carbon dioxide fire extinguisher | 1 | Ea | 388 | 0.65 | 0.35 | 1 | 252.2 | 135.8 | 388 | 100% | 500 | 10 | 510 | -122
| SUB-TOTAL ITEM NO. B12-10 00 00 | xxx | xxx |  |  |  |  | 434.075 | 196.425 | 630.5 |  |  |  | 760 | -129.5

## PUMP RM-3
PUMP RM3
| B O Q |  |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR)
DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | UNIT PRICE(SR) -10% ADVANCE PAYMENT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative | Percentage | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 28-ELECTRONIC SAFETY AND SECURITY
Fire Detection and Alarm
Detection and initiation devices
Supply, installation, testing and commissioning of intelligent, addressable type fire alarm detectors and initiating devices as shown on the Contract drawings and specified in the Contract documents complete with all mounting accessories including boxes, connectors and terminations.
Smoke detector - photoelectric, addressable, self diagnostic, self address, weather proof | 2 | Ea | 339.5 | 305.55 | 0 | 2 | 2 | 0 | 679 | 679 | 1 | 120 | 80 | 400 | 279
Addressable manual fire alarm pull station, weather proof | 1 | Ea | 291 | 261.9 | 0 | 1 | 1 | 0 | 291 | 291 | 1 | 160 | 80 | 240 | 51
Fire alarm cables - fire resistant cable, 300V/500V, red sheath with low emission of smoke, halogen free, thermoplastic material
To include for the procurement, supply, factory testing, delivery to Site, installation, testing and commissioning of the cables, termination materials and all cable support and wiring, identification accessories.
2C x 2.5 mm², Stranded plain copper wire or solid conductor, overall shield with drain wire for NAC Loop | 80 | m | 24.25 | 21.825 | 0 | 80 | 80 | 0 | 1940 | 1940 | 100% | 8 | 0 | 640 | 1300
Fire alarm cable conduit, all JB boxes, fittings and accessories for cable installations
To include for the procurement, supply, installation of PVC conduits and flexible metallic conduits for fire cables, junction boxes, fittings, accessories and all other relevant items or Works to complete fully Fire alarm detection system installations.
20 mm diameter, PVC conduits | 0 | m | 24.25 | 21.825 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
SUB-TOTAL ITEM NO. B13-28 00 00 | xxx | xxx | [5 empty] | 0 | 2910 | 2910 |  |  |  | 1280 | 1630
(TO BE CARRIED TO COMPOSITE SUMMARY)
OWNER |  |  | CONSULTANT |  |  |  |  | CONTRACTOR

## PUMP-R3-EXT
PUMP03
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR) |  |  | Percentage
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative |  | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 10 - SPECIALTIES
1.0 | Fire Extinguishers
a. | Multipurpose dry chemical type, UL rated ABC
Includes mounting brackets, fasteners, service tags, fully charged and ready to use extinguishers.
a.1 | FE-1, 6 kg, Multi-purpose fire extinguisher | 1 | Ea | 242.5 | 0.75 | 0.25 | 1 | 181.875 | 60.625 | 242.5 | 100% | 240 | 10 | 250 | -7.5
a.2 | FE-2, 6 kg, carbon dioxide fire extinguisher | 1 | Ea | 388 | 0.65 | 0.35 | 1 | 252.2 | 135.8 | 388 | 100% | 500 | 10 | 510 | -122
b. | Automatic fire extinguisher
b.1 | AFE-5, 30 kg, multi purpose fire extinguisher, ceiling mounted | 12 | Ea | 630.5 | 7.8 | 4.2 | 12 | 4917.9 | 2648.1 | 7566 | 100% | 435 | 10 | 5340 | 2226
| SUB-TOTAL ITEM NO. B13-10 00 00 | xxx | xxx |  |  |  |  | 5351.975 | 2844.525 | 8196.5 |  |  |  | 6100 | 2096.5

## PUMP02
PUMP 02
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR)
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative | Percentage | Actual price | accessories | Actual Labour charge | Total AP+LC | Profit
DIVISION 21 - FIRE SUPPRESSION
1.0 | General-Duty Valves for Water-Based Fire-Suppression Piping
a. | Gate valve, UL and FM global approved
Supply and installation of valves including all fixings, supports, all other accessories and associated Works.
a.1 | 200 mm diameter | 10 | Ea | 5335 | 9 | 1 | 10 | 48015 | 5335 | 53350 | 100% | 4000 | 300 | 300 | 46000 | 7350
b. | Alarm check valve, UL and FM global approved
b.2 | 200 mm diameter | 1 | Ea | 8245 | 0.9 | 0.1 | 1 | 7420.5 | 824.5 | 8245 | 100% | 1800 | 200 | 100 | 2100 | 6145
c. | Check valve, UL and FM global approved
c.1 | 200 mm diameter | 2 | Ea | 4850 | 1.8 | 0.2 | 2 | 8730 | 970 | 9700 | 100% | 2500 | 150 | 100 | 5500 | 4200
c.2 | 50 mm diameter | 1 | Ea | 2425 | 0.9 | 0.1 | 1 | 2182.5 | 242.5 | 2425 | 100% | 850 | 100 | 100 | 1050 | 1375
d. | Zone control valve assembly
d.1 | 65 mm diameter | 1 | Ea | 4365 | 0.8 | 0.2 | 1 | 3492 | 873 | 4365 | 100% | 2800 | 300 | 100 | 3200 | 1165
e. | Flow meter
e.1 | 150 mm diameter | 1 | Ea | 8730 | 0.9 | 0.1 | 1 | 7857 | 873 | 8730 | 100% | 0 | 0 | 0 | 0 | 8730
f. | Flexible pipe connection
f.1 | 50 mm diameter | 2 | Ea | 1746 | 0 | 2 | 2 | 0 | 3492 | 3492 | 100% | 0 | 0
f.2 | 150 mm diameter | 8 | Ea | 2619 | 0 | 8 | 8 | 0 | 20952 | 20952 | 100% | 0 | 0 | 0 | 0 | 20952
g. | Strainer, Y type | [10 empty] | 0 | 0 | 0 | 0 | 0
g.1 | 200 mm diameter | 1 | Ea | 3589 | 0 | 1 | 1 | 0 | 3589 | 3589 | 100% | 0 | 0 | 0 | 0 | 3589
g.2 | 50 mm diameter | 1 | Ea | 2134 | 0 | 1 | 1 | 0 | 2134 | 2134 | 100% | 0 | 0 | 0 | 0 | 2134
2.0 | Wet-Pipe Sprinkler Systems
a. | Black steel fire water pipes
Supply and installation of black steel pipe seamless type as per ASTM A53 including supports, hangers, fixing, fitting, all other accessories and associated Works as per Contract drawings and specifications.
a.1 | 25 mm diameter | 5 | m | 53.35 | 4.5 | 0.5 | 5 | 240.075 | 26.675 | 266.75 | 100% | 15 | 7.5 | 0 | 112.5 | 154.25
a.2 | 32 mm diameter | 5 | m | 63.05 | 4.5 | 0.5 | 5 | 283.725 | 31.525 | 315.25 | 100% | 20 | 10 | 0 | 150 | 165.25
a.3 | 40 mm diameter | 5 | m | 77.6 | 4.5 | 0.5 | 5 | 349.2 | 38.8 | 388 | 100% | 24 | 12 | 0 | 180 | 208
a.4 | 50 mm diameter | 15 | m | 95.06 | 13.528 | 1.472 | 15 | 1285.9717 | 139.9283 | 1425.9 | 100% | 28 | 14 | 0 | 630 | 795.9
a.5 | 150 mm diameter | 15 | m | 344.35 | 13.425 | 1.575 | 15 | 4622.8988 | 542.3512 | 5165.25 | 100% | 170 | 90 | 0 | 3900 | 1265.25
a.6 | 200 mm diameter | 50 | m | 295.85 | 45 | 5 | 50 | 13313.25 | 1479.25 | 14792.5 | 100% | 190 | 85 | 0 | 13750 | 1042.5
b. | Fire water sprinkler head
Sprinkler Head, UL listed FM approved, chrome-plated, bronze and factory painted; Shall be of one manufacturer. (No mixing of sprinkler brands shall be permitted).
b.1 | Type, upright | 18 | Ea | 33.95 | 16.2 | 1.8 | 18 | 549.99 | 61.11 | 611.1 | 100% | 19 | 5 | 100 | 2232 | -1620.9
3.0 | Fire Pumps
a. | Electric-drive, centrifugal fire pumps
Supply and installation of Electric-drive, centrifugal fire pumps including all required accessories, piping, valves, strainers, check valves, control panels and all the fittings required, instrumentation devices, dismantling joint, flow meters and other associated Works and complete pipe connections as detailed in Contract drawings. Works include testing and commissioning.
a.1 | 1500 GPM, 130 PSI | 1 | Ea | 150738 | 0.85 | 0.15 | 1 | 128127.3 | 22610.7 | 150738 | 100% | 100000 | 10000 | 5000 | 115000 | 35738
b. | Electric drive jockey pump
Supply and installation of fire electrical jockey pump capacity 50 gpm & 130 Psi (1duty) with enclosure including all required accessories, piping, valves, strainers, check valves, control panels and all the fittings required, instrumentation devices, dismantling joint, flow meters and other associated Works and complete pipe connections as detailed in Contract drawings. Works include testing and commissioning.
b.1 | 50 GPM, 130 PSI | 1 | Ea | 18333 | 0.85 | 0.15 | 1 | 15583.05 | 2749.95 | 18333 | 100% | 15000 | 2000 | 500 | 17500 | 833
c. | Diesel Fire pump
Supply and installation of Diesel Fire pump including all required accessories, piping, valves, strainers, check valves, control panels and all the fittings required, instrumentation devices, dismantling joint, flow meters and other associated Works and complete pipe connections as detailed in Contract drawings. Works include testing and commissioning.
c.1 | 1500 GPM, 130 PSI | 1 | Ea | 232800 | 0.85 | 0.15 | 1 | 197880 | 34920 | 232800 | 100% | 150000 | 8000 | 10000 | 168000 | 64800
| SUB-TOTAL ITEM NO. B12-21 00 00 | xxx | xxx |  |  |  |  | 439932.4604 | 101885.2896 | 541817.75 |  |  |  |  | 211304.5 | 159021.25
(TO BE CARRIED TO COMPOSITE SUMMARY)
| OWNER | CONSULTANT | [5 empty] | CONTRACTOR

## GUARD RM
GUARD ROOM
| B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR) |  |  | Percentage
DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative |  | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 28-ELECTRONIC SAFETY AND SECURITY
Fire Detection and Alarm
Fire alarm control panel (FACP)
Supply, installation, testing and commissioning of a microprocessor based, addressable fire alarm control panel, complete with Chassis, 640-Character backlit LCD display, QWERTY programming and control keypad, loop cards, zone and input/output modules, supervisory devices, auxiliary relays, network capability modules, battery, battery charger, printer, internal alarm, interface contacts and all accessories and hardware as shown on the Contract drawings and specified in the Contract documents and to complete the fully functional, operable, reliable and maintainable fire alarm system.
Microprocessor based, addressable FACP, 5 loop type | 1 | Ea | 22795 | 0.65 | 0.35 | 1 | 14816.75 | 7978.25 | 22795 | 100% | 16900 | 80 | 16980 | 5815
Fire alarm repeater panel (FARP) | 1 | Ea | 12998 | 0.65 | 0.35 | 1 | 8448.7 | 4549.3 | 12998 | 100% | 5800 | 80 | 5880 | 7118
Power supply unit, batteries and battery chargers | 1 | Ea | 4365 | 0 | 1 | 1 | 0 | 4365 | 4365 | 100%
Supply, selection and calculation, installation, testing and commissioning of FACP power supply unit, batteries for at least 24 hours during the normal operations and 15 mins under emergency full loaded condition. Provide separate combination of power Supply and battery enclosure when large batteries are required and not be able embedded inside FACP panel.
Detection and initiation devices
Supply, installation, testing and commissioning of intelligent, addressable type fire alarm detectors and initiating devices as shown on the Contract drawings and specified in the Contract documents complete with all mounting accessories including boxes, connectors and terminations.
Smoke detector - photoelectric, addressable, self diagnostic, self address | 2 | Ea | 339.5 | 1.3 | 0.7 | 2 | 441.35 | 237.65 | 679 | 100% | 120 | 80 | 400 | 279
Heat detector - rate of rise type with fix temperature | 1 | Ea | 339.5 | 0 | 1 | 1 | 0 | 339.5 | 339.5 | 100% | 110 | 80 | 190 | 149.5
Addressable manual fire alarm pull station | 1 | Ea | 291 | 0.65 | 0.35 | 1 | 189.15 | 101.85 | 291 | 100% | 160 | 80 | 240 | 51
Notification appliances
Supply, installation, testing and commissioning of visual and sound alarm devices as shown on the Contract drawings and specified in the Contract documents complete with all mounting accessories including boxes and terminations.
Bells, indoor with strobe lights / beacons - red body, red lens for fire alarm | 1 | Ea | 388 | 0.65 | 0.35 | 1 | 252.2 | 135.8 | 388 | 100% | 220 | 80 | 300 | 88
Bells, indoor with strobe lights / beacons - red body, red lens for fire alarm, weather proof | 2 | Ea | 436.5 | 0 | 2 | 2 | 0 | 873 | 873 | 100% | 250 | 80 | 660 | 213
Fire alarm cables - fire resistant cable, 300V/500V, red sheath with low emission of smoke, halogen free, thermoplastic material
To include for the procurement, supply, factory testing, delivery to Site, installation, testing and commissioning of the cables, termination materials and all cable support and wiring, identification accessories.
2C x 2.5 mm², Stranded plain copper wire or solid conductor, overall shield with drain wire for SLC loop | 120 | m | 24.25 | 114 | 6 | 120 | 2764.5 | 145.5 | 2910 | 100% | 8 | 0 | 960 | 1950
2C x 2.5 mm², Stranded plain copper wire or solid conductor, overall shield with drain wire for NAC Loop | 30 | m | 24.25 | 28.5 | 1.5 | 30 | 691.125 | 36.375 | 727.5 | 100% | 8 | 0 | 240 | 487.5
Fire alarm cable conduit, all JB boxes, fittings and accessories for cable installations
To include for the procurement, supply, installation of PVC conduits and flexible metallic conduits for fire cables, junction boxes, fittings, accessories and all other relevant items or Works to complete fully Fire alarm detection system installations.
20 mm diameter, PVC conduits | 0 | m | 24.25 | 0 | 0 | 0 | 0 | 0 | 0
SUB-TOTAL ITEM NO. B10-28 00 00 | xxx | xxx |  |  |  |  | 27603.775 | 18762.225 | 46366 |  |  |  | 25850 | 16151
(TO BE CARRIED TO COMPOSITE SUMMARY)
OWNER |  | CONSULTANT |  |  |  |  | CONTRACTOR

## GUARD-RM-EXT
GUARD
SECTION 2- SCHEDULE OF QUANTITIES AND PRICES |  | B O Q |  |  | THE ACTUAL QTY |  |  | AMOUNT (SR) |  |  | Percentage
PAY ITEM NO. | DESCRIPTION OF ITEM | ESTIMATED QUANTITY | UNIT | UNIT PRICE(SR) EXCL. VAT | Previous QTY | Current QTY | Cumulative QTY | Previous | Current | Cumulative |  | Actual price | Actual Labour charge | Total AP+LC | Profit
DIVISION 10 - SPECIALTIES
1.0 | Fire Extinguishers
a. | Multipurpose dry chemical type, UL rated ABC
Includes mounting brackets, fasteners, service tags, fully charged and ready to use extinguishers.
a.1 | FE-1, 6 kg, Multi-purpose fire extinguisher | 1 | Ea | 242.5 | 0.75 | 0.25 | 1 | 181.875 | 60.625 | 242.5 | 100% | 240 | 10 | 250 | -7.5
a.2 | FE-2, 6 kg, carbon dioxide fire extinguisher | 1 | Ea | 388 | 0.65 | 0.35 | 1 | 252.2 | 135.8 | 388 | 100% | 500 | 10 | 510 | -122
| SUB-TOTAL ITEM NO. B10-10 00 00 | xxx | xxx |  |  |  |  | 434.075 | 196.425 | 630.5 |  |  |  | 760 | -129.5

## حصر الأنابيب
CONTRACT QUANTITES
Pipe Dia(inch) | JUN-T1 | JUN-T2 | SUPERVISOR | ISOLATED | SENIOR | ADMIN | RECREATION | SERVICE | PUMP RM-2 |  | CONTRACT TOTAL QTY | HALF QTY | PREVIOUS SUPPLIED | NEW SUPPLY | TOTAL SUPPLY
1 | 2550 | 520 | 1305 | 250 | 1485 |  | 1080 | 2100 | 5 |  | 9295 | 4647.5 | 6864 | 2304 | 9168 | 127 | 21.1667
1.25 | 375 | 120 | 90 | 10 | 90 |  | 325 | 535 | 5 |  | 1550 | 775 | 1164 | 240 | 1404 | 146 | 24.3333
1.5 | 276 | 20 | 120 | 40 | 135 | 40 | 130 | 285 | 5 |  | 1051 | 525.5 | 762 | 246 | 1008 | 43 | 7.1667
2 | 90 | 130 | 60 | 30 | 90 | 30 | 60 | 110 | 15 |  | 615 | 307.5 | 426 | 144 | 570 | 45 | 7.5
2.5 | 30 | 190 | 300 | 70 | 345 | 30 | 130 | 130 |  |  | 1225 | 612.5 | 900 | 0 | 900 | 325 | 54.1667
3 | 30 | 50 | 150 | 40 | 180 |  | 40 | 200 |  |  | 690 | 345 | 708 | 174 | 882 | -192 | -32
4 | 450 | 30 | 30 | 10 | 30 | 10 | 80 | 180 |  |  | 820 | 410 | 2442 | 0 | 2442 | -1622 | -270.3333
6 | 120 | 40 | 90 | 40 | 120 |  | 20 | 40 | 15 |  | 485 | 242.5 | 354 | 0 | 354 | 131 | 21.8333
8 | [8 empty] | 50 |  | 50 | 0 |  |  | 0
Pipe Dia(inch) | JUN-T1 | JUN-T2 | SUPERVISOR | ISOLATED | SENIOR | ADMIN | RECREATION | SERVICE | TOTAL
1 | 651 | 130 | 326 | 62.5 | 371 |  | 275 | 525 | 2340.5
1.25 | 97 | 30 | 22 | 2.5 | 22.5 |  | 82 | 134 | 390
1.5 | 65 | 5 | 30 | 10 | 33.5 | 10 | 33 | 72 | 258.5 | 369 | 6KG FIRE EXTINGUISHER
2 | 40 | 33 | 15 | 7.5 | 22.5 | 7.5 | 15 | 27.5 | 168
2.5 | 20 | 48 | 55 | 17.5 | 86.5 | 7.5 | 33 | 33 | 300.5
3 | 30 | 45 | 100 | 20 | 120 | 0 | 10 | 50 | 375
4 | 227 | 15 | 15 | 2.5 | 15 | 5 | 40 | 90 | 409.5
6 | 17 | 20 | 22.5 | 10 | 30 |  | 5 | 10 | 114.5
8 | [8 empty] | 0
Pipe Dia(inch) | JUN-T1 | JUN-T2 | SUPERVISOR | ISOLATED | SENIOR | ADMIN | RECREATION | SERVICE | TOTAL
1 | -1899 | -390 | -979 | -187.5 | -1114 | 0 | -805 | -1575 | -6949.5
1.25 | -278 | -90 | -68 | -7.5 | -67.5 | 0 | -243 | -401 | -1155
1.5 | -211 | -15 | -90 | -30 | -101.5 | -30 | -97 | -213 | -787.5
2 | -50 | -97 | -45 | -22.5 | -67.5 | -22.5 | -45 | -82.5 | -432
2.5 | -10 | -142 | -245 | -52.5 | -258.5 | -22.5 | -97 | -97 | -924.5
3 | 0 | -5 | -50 | -20 | -60 | 0 | -30 | -150 | -315
4 | -223 | -15 | -15 | -7.5 | -15 | -5 | -40 | -90 | -410.5
6 | -103 | -20 | -67.5 | -30 | -90 | 0 | -15 | -30 | -355.5
8 | [8 empty] | 0

## حصر الكيبل
CONTRACT QUANTITES
2.5MM CABLE | JUN-T1 | JUN-T2 | SUPERVISOR | ISOLATED | SENIOR | ADMIN | RECREATION | SERVICE | GUARD RM | PUMP RM-1 | PUMP RM-2 | PUMP RM-3 | TOTAL
SLC | 3915 | 1600 | 2400 | 800 | 3600 | 800 | 2000 | 2000 | 120 | 80 | 80 | 80
NAC | 1845 | 800 | 1200 | 400 | 1800 | 400 | 800 | 800 | 30
TOTAL | 5760 | 2400 | 3600 | 1200 | 5400 | 1200 | 2800 | 2800 | 150 | 80 | 80 | 80 | 25550
83.7705
9.1803
|  |  | ACTUAL SUPPLIED QUANTITY |  |  | 50 ROLL X 305M= |  | 15250
[6 empty] | 16 ROLL X 305M= |  | 4880
[6 empty] | 04 ROLL X 305 |  | 1220
[6 empty] | 06 ROLL X 305 |  | 1830
[6 empty] | 16 ROLL X 305 |  | 4880
[6 empty] | 3 ROLL X 305 |  | 915
[6 empty] | TOTAL |  | 28975
2.5MM CABLE | JUN-T1 | JUN-T2 | SUPERVISOR | ISOLATED | SENIOR | ADMIN | RECREATION | SERVICE | GUARD RM | PUMP RM-1 | PUMP RM-2 | PUMP RM-3 | TOTAL
SLC | 3915 | 1600 | 2400 | 800 | 3600 | 800 | 2000 | 1200+800 | 120 | 80 | 80 | 80
NAC | 1845 | 800 | 1200 | 400 | 1800 | 400 | 800 | 800 | 30
TOTAL | 5760 | 2400 | 3600 | 1200 | 5400 | 1200 | 2800 | 2800 | 150 | 80 | 80 | 80 | 25550
0
| 395 | [5 empty] | 2000 + 150 +80= 2230
|  |  | ACTUAL INSTALLED FLOOR |  |  | NEW INSTALLED
OLD INSTALLED
BLDG. FLOOR | JUN-T1 | JUN-T2 | SUPERVISOR | ISOLATED | SENIOR | ADMIN | RECREATION | SERVICE | GUARD RM | PUMP RM-1 | PUMP RM-2 | PUMP RM-3
GR | X3 | X2 | X3 | X1 | X3 | X1 | X1 |  | X1
1st | X3 | X2 | X3 | X1 | X3 | X1
2nd | X3 | X2 | OLDX2 + NEW X1 |  | X3
ROOF | X3 | NEW X2 | OLDX2 + NEW X1 |  | X3
DEVICE TYPE | OLD.SPLYD | NEW.SPLYD | JN-1 | JN-2 | ADMIN | SPRVSR | SENIOR | REMAIN
SMOKE | 742 | 60 | 157 | 244 | 52 | 0 | 197 | 32
HEAT | 30 | 4 | 15 | 6 | 2 | 0 | 7 | 4
MCP | 45 | 0 | 30 | 12 | 3 | 0 | 0 | 0
WP-MCP | 20 | 7 | 14 | 4 | 0 | 2 | 0 | 0
SIREN | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 15
WP-SIREN | 20 | 27 | 13 | 7 | 0 | 0 | 0 | 27
PANELS

## المصروفات الإضافية
سجل المصروفات الإضافية للمشروع
أدخل كل مصروف في صف مستقل. اترك خانة المبلغ فارغة إذا لم يتم تسجيل المصروف بعد.
التاريخ | الفئة | البيان / الغرض | المورد أو المستفيد | رقم المستند | المبلغ (ر.س) | حالة الاعتماد | ملاحظات | الشهر | كود التكلفة
1مايو 2024 | مرتبات الاستاف | مرتب المهندس عصام | مهندس عصام |  | 84000 |  | حتي ابريل 2025 7000X | 1مايو 2024
1مايو 2024 | مرتبات الاستاف | مرتب المهندس إبراهيم | مهندس إبراهيم |  | 94000 |  | 12 month per 7000+2 month per 5000 | 1مايو 2024 |  | 84
1مايو 2024 | السكن | سكن المهندسين | المهندسين |  | 37500 |  | سكن شقة مفروشة لفترة 15 شهر في 2500 | 1مايو 2024
1مارس 2025 | مرتبات الاستاف | مرتب مهندس عثمان | م عثمان |  | 109000 |  | 12شهر بحساب 5000 ريال و7 شهور بحساب 7000 | 1مارس 2025
1مارس 2025 | السكن | سكن المهندس عثمان | م عثمان |  | 30000 |  | سكن شقة مفروشة لفترة 12 شهر في 2500 | 1مارس 2025
1مايو 2024 | الترحيل والنقل | م إبراهيم وعثمان | إبراهيم وعثمان |  | 90000 |  | نقل المهندسين | 1مايو 2024
1مايو 2024 | السكن | سكن العمال شقتين | عمال المشروع |  | 60000 |  | سكن عمال | 1مايو 2024
1مايو 2024 | معدات وأدوات | ترحيل مواد وايجار معدات | مصاريف المشروع |  | 25000 |  | مصاريف المشروع | 1مايو 2024
1مايو 2024 | مصاريف مكتبية | مصاريف المكتب | مصاريف مكتبية |  | 20000 |  | طباعة وضيافة ومواد مكتبية | 1مايو 2024

## ملخص التكاليف
ملخص تكاليف مشروع سبارك
مصدر التكلفة | المواد (ر.س) | العمالة (ر.س) | إجمالي التكلفة المباشرة (ر.س) | الربح الحسابي قبل المصروفات (ر.س) | هامش الربح الحسابي | Profit الفعلي من الورقة (ر.س) | المبلغ الكلي للمبني | التكلفة الكلية عمالة ومواد | الربح الاسمي
JUN-T1 E | 389778 | 83280 | 473058 | 822424.2 | 57.52% | 349366.2 | 822424.2 | 473058 | 349366.2
JUN-T1-EXT | 49728 | 2160 | 51888 | 76242 | 68.06% | 24354 | 76242 | 51888 | 24354
JUN-T1 | 413250 | 147900 | 561150 | 759495.45 | 73.88% | 110628.45 | 759495.45 | 648867 | 110628.45
JUN-T2 E | 92788 | 24480 | 117268 | 218269.4 | 53.73% | 101001.4 | 218269.4 | 117268 | 101001.4
JUN-T2-EXT | 11168 | 480 | 11648 | 15617 | 74.59% | 3969 | 15617 | 11648 | 3969
JUN-T2 | 147688 | 48600 | 196288 | 298071.3 | 65.85% | 77173.3 | 298071.3 | 220898 | 77173.3
SUPERVISOR -E | 145662 | 41040 | 186702 | 345737.1 | 54% | 159035.1 | 345737.1 | 186702 | 159035.1
SUPERVISOR-EXT | 20118 | 810 | 20928 | 27790.5 | 75.31% | 6862.5 | 27790.5 | 20928 | 6862.5
SUPERVISOR | 210048 | 88200 | 298248 | 446714.1 | 66.76% | 105963.6 | 446714.1 | 340750.5 | 105963.6
ISOLATE - E | 40590 | 8800 | 49390 | 94284 | 52.38% | 44894 | 94284 | 49390 | 44894
ISOLATED-EXT | 5170 | 200 | 5370 | 7432 | 72.26% | 2062 | 7432 | 5370 | 2062
ISOLATED | 52467 | 20100 | 72567 | 114358.15 | 63.46% | 29941.15 | 114358.15 | 84417 | 29941.15
SENIOR - E | 165804 | 45120 | 210924 | 406992.6 | 51.83% | 196068.6 | 406992.6 | 210924 | 196068.6
SENIOR-EXT | 14088 | 540 | 14628 | 18072 | 80.94% | 3444 | 18072 | 14628 | 3444
SENIOR | 226341 | 100500 | 326841 | 492197.4 | 66.4% | 116163.9 | 492197.4 | 376033.5 | 116163.9
ADMIN -E | 61668 | 5440 | 67108 | 146246.9 | 45.89% | 79138.9 | 146246.9 | 67108 | 79138.9
ADMIN-EXT | 3534 | 140 | 3674 | 4995.5 | 73.55% | 1321.5 | 4995.5 | 3674 | 1321.5
ADMIN | 105650 | 6200 | 111850 | 156790.8 | 71.34% | 57140.8 | 156790.8 | 99650 | 57140.8
RECREATION - E | 61924 | 12320 | 74244 | 150282.1 | 49.4% | 93018.1 | 150282.1 | 57264 | 93018.1
RECREATION-EXT | 13032 | 490 | 13522 | 14850 | 91.06% | 1328 | 14850 | 13522 | 1328
RECREATION | 98534 | 36000 | 134534 | 235152.25 | 57.21% | 72878.25 | 235152.25 | 162274 | 72878.25
SERVICE - E | 114296 | 31120 | 145416 | 297644.5 | 48.86% | 152228.5 | 297644.5 | 145416 | 152228.5
SERVICE-EXT | 32994 | 1260 | 34254 | 36050 | 95.02% | 1796 | 36050 | 34254 | 1796
SERVICE | 252045 | 99700 | 351745 | 735706.85 | 47.81% | 323356.85 | 735706.85 | 412350 | 323356.85
PUMP RM-1 | 1040 | 240 | 1280 | 2910 | 43.99% | 1630 | 2910 | 1280 | 1630
PUMP-R1-EXT | 11615 | 270 | 11885 | 16393 | 72.5% | 4508 | 16393 | 11885 | 4508
PUMP RM-2 | 1320 | 240 | 1560 | 11640 | 13.4% | 10080 | 11640 | 1560 | 10080
PUMP-R2-EXT | 740 | 20 | 760 | 630.5 | 120.5% | -129.5 | 630.5 | 760 | -129.5
PUMP RM-3 | 1040 | 240 | 1280 | 2910 | 43.99% | 1630 | 2910 | 1280 | 1630
PUMP-R3-EXT | 5960 | 140 | 6100 | 8196.5 | 74.42% | 2096.5 | 8196.5 | 6100 | 2096.5
PUMP02 | 328557 | 20800 | 349357 | 541817.75 | 64.48% | 330513.25 | 541817.75 | 211304.5 | 330513.25
GUARD RM | 25130 | 720 | 25850 | 46366 | 55.75% | 20516 | 46366 | 25850 | 20516
GUARD-RM-EXT | 740 | 20 | 760 | 630.5 | 120.5% | -129.5 | 630.5 | 760 | -129.5
الإجمالي المباشر | 3104507 | 827570 | 3932077 | 6552910.35 | 1.0092 | 2483848.85 | 6552910.35 | 4069061.5 | 2483848.85
تصنيف المصروفات الإضافية | المبلغ المسجل (ر.س) | النسبة من المصروفات الإضافية
ترحيل المواد | 0 | 0%
مصاريف مكتبية | 20000 | 3.64%
مرتبات الاستاف | 287000 | 52.23%
السكن | 127500 | 23.2%
الترحيل والنقل | 90000 | 16.38%
اتصالات وإنترنت | 0 | 0%
معدات وأدوات | 25000 | 4.55%
رسوم وتصاريح | 0 | 0%
تأمين وضمانات | 0 | 0%
مصروفات أخرى | 0 | 0%
إجمالي المصروفات الإضافية | 549500

## دليل الاستخدام
دليل استخدام نموذج الربحية
الغرض | هذا النموذج يربط قيمة الأعمال المنجزة وتكاليف المواد والعمالة الموجودة في أوراق المستخلص مع سجل مستقل للمصروفات الإضافية.
الخطوة 1 | استخدم ورقة «المصروفات الإضافية» لتسجيل كل مصروف في صف مستقل، مع التاريخ والفئة والبيان والمبلغ وحالة الاعتماد.
الخطوة 2 | استخدم القوائم المنسدلة لاختيار فئة المصروف وحالة اعتماده. لا تكتب فوق الخلايا التي تحتوي على صيغ.
الخطوة 3 | راجع «ملخص التكاليف» لمعرفة التكلفة المباشرة حسب مصدر التكلفة وتوزيع المصروفات الإضافية حسب الفئة.
الخطوة 4 | استخدم «لوحة الربحية» للعرض الإداري. الربح الصافي = قيمة الأعمال المنجزة – التكلفة المباشرة – المصروفات الإضافية.
ملاحظة محاسبية | المصروفات الإضافية تكون صفراً حتى يتم إدخالها. لذلك لا يمثل الربح الظاهر حالياً صافي الربح النهائي إلا بعد استكمال التسجيل والمراجعة.
ملاحظة على المستخلص | التحليل مبني على قيم المستخلص والحقول Actual price وActual Labour charge وProfit الموجودة في أوراق الأعمال، مع إبقاء الأوراق الأصلية دون حذف.